## Building-cost.net
Direct Cost Items (Class 4 see below) | [8 empty] | Class 5 Average Standard
Item Name | Materials | Labor | Equipment | Total | Rate $/HR | Labor Hours | Weeks | Days | Item Name | Materials | Labor | Equipment | Total | Rate $/HR | Labor Hours | 40hr Weeks | 8hr Working Days
Excavation | 0 | 6540 | 2542 | 9082 | 90 | 72.6667 | 1.8167 | 9.0833 | Excavation | ---- | 4194 | 1630 | 5824 | 90 | 46.6 | 1.165 | 5.825
Foundation, Piers, Flatwork | 33196 | 33808 | 8051 | 75055 | 75 | 450.7733 | 11.2693 | 56.3467 | Foundation, Piers, Flatwork | 23735 | 24170 | 5764 | 53669 | 75 | 322.2667 | 8.0567 | 40.2833
Insulation | 8368 | 3640 | 0 | 12008 | 75 | 48.5333 | 1.2133 | 6.0667 | Insulation | 7295 | 3172 | ---- | 10467 | 75 | 42.2933 | 1.0573 | 5.2867
Rough Hardware | 1580 | 1617 | 364 | 3561 | 75 | 21.56 | 0.539 | 2.695 | Rough Hardware | 1376 | 1407 | 320 | 3103 | 75 | 18.76 | 0.469 | 2.345
Framing | 51077 | 47529 | 0 | 98606 | 75 | 633.72 | 15.843 | 79.215 | Framing | 44517 | 41423 | ---- | 85940 | 75 | 552.3067 | 13.8077 | 69.0383
Exterior Finish | 32983 | 12937 | 6129 | 52049 | 75 | 172.4933 | 4.3123 | 21.5617 | Exterior Finish | 25629 | 10052 | 4762 | 40443 | 75 | 134.0267 | 3.3507 | 16.7533
Exterior Trim | 2361 | 2806 | 579 | 5746 | 75 | 37.4133 | 0.93533 | 4.6767 | Exterior Trim | 1833 | 2181 | 449 | 4463 | 75 | 29.08 | 0.727 | 3.635
Doors | 9043 | 4012 | 0 | 13055 | 75 | 53.4933 | 1.3373 | 6.6867 | Doors | 7027 | 3118 | ---- | 10145 | 75 | 41.5733 | 1.0393 | 5.1967
Windows | 9095 | 2883 | 0 | 11978 | 75 | 38.44 | 0.961 | 4.805 | Windows | 7068 | 2240 | ---- | 9308 | 75 | 29.8667 | 0.74667 | 3.7333
Roofing, Soffit, Fascia | 30318 | 13544 | 0 | 43862 | 75 | 180.5867 | 4.5147 | 22.5733 | Roofing, Soffit, Fascia | 23559 | 10525 | ---- | 34084 | 75 | 140.3333 | 3.5083 | 17.5417
Finish Carpentry | 4076 | 11285 | 0 | 15361 | 75 | 150.4667 | 3.7617 | 18.8083 | Finish Carpentry | 2562 | 7090 | ---- | 9652 | 75 | 94.5333 | 2.3633 | 11.8167
Interior Wall Finish | 15438 | 15333 | 0 | 30771 | 75 | 204.44 | 5.111 | 25.555 | Interior Wall Finish | 9698 | 9635 | ---- | 19333 | 75 | 128.4667 | 3.2117 | 16.0583
Lighting Fixtures | 6984 | 1428 | 0 | 8412 | 75 | 19.04 | 0.476 | 2.38 | Lighting Fixtures | 4387 | 897 | ---- | 5284 | 75 | 11.96 | 0.299 | 1.495
Painting | 9178 | 13905 | 0 | 23083 | 75 | 185.4 | 4.635 | 23.175 | Painting | 5766 | 8736 | ---- | 14502 | 75 | 116.48 | 2.912 | 14.56
Carpet, Flooring | 18980 | 9010 | 0 | 27990 | 75 | 120.1333 | 3.0033 | 15.0167 | Carpet, Flooring | 11754 | 5580 | ---- | 17334 | 75 | 74.4 | 1.86 | 9.3
Bath Accessories | 2656 | 1084 | 0 | 3740 | 75 | 14.4533 | 0.36133 | 1.8067 | Bath Accessories | 1574 | 642 | ---- | 2216 | 75 | 8.56 | 0.214 | 1.07
Shower & Tub Enclosures | 1732 | 942 | 0 | 2674 | 75 | 12.56 | 0.314 | 1.57 | Shower & Tub Enclosures | 1027 | 558 | ---- | 1585 | 75 | 7.44 | 0.186 | 0.93
Plumbing Fixtures | 15593 | 4945 | 0 | 20538 | 75 | 65.9333 | 1.6483 | 8.2417 | Plumbing Fixtures | 9239 | 2930 | ---- | 12169 | 75 | 39.0667 | 0.97667 | 4.8833
Plumbing Rough-in | 7738 | 12576 | 0 | 20314 | 75 | 167.68 | 4.192 | 20.96 | Plumbing Rough-in | 4586 | 7452 | ---- | 12038 | 75 | 99.36 | 2.484 | 12.42
Wiring | 9436 | 11408 | 0 | 20844 | 75 | 152.1067 | 3.8027 | 19.0133 | Wiring | 5924 | 7169 | ---- | 13093 | 75 | 95.5867 | 2.3897 | 11.9483
Built In Appliances | 8316 | 753 | 0 | 9069 | 75 | 10.04 | 0.251 | 1.255 | Built In Appliances | 4928 | 447 | ---- | 5375 | 75 | 5.96 | 0.149 | 0.745
Cabinets | 17095 | 3485 | 0 | 20580 | 75 | 46.4667 | 1.1617 | 5.8083 | Cabinets | 10129 | 2066 | ---- | 12195 | 75 | 27.5467 | 0.68867 | 3.4433
Countertops | 5197 | 2826 | 0 | 8023 | 75 | 37.68 | 0.942 | 4.71 | Countertops | 3080 | 1674 | ---- | 4754 | 75 | 22.32 | 0.558 | 2.79
Central Heating and Cooling | 8269 | 10114 | 0 | 18383 | 75 | 134.8533 | 3.3713 | 16.8567 | Central Heating and Cooling | 8269 | 10114 | ---- | 18383 | 75 | 134.8533 | 3.3713 | 16.8567
Fire Sprinklers | 4719 | 4948 | 0 | 9667 | 75 | 65.9733 | 1.6493 | 8.2467 | Fire Sprinklers | 4784 | 5016 | ---- | 9800 | 75 | 66.88 | 1.672 | 8.36
Garage Door | 4252 | 1734 | 0 | 5986 | 75 | 23.12 | 0.578 | 2.89 | Garage Door | 2835 | 1156 | ---- | 3991 | 75 | 15.4133 | 0.38533 | 1.9267
Fireplace | 1347 | 275 | 0 | 1622 | 75 | 3.6667 | 0.091667 | 0.45833 | Fireplace | 1347 | 275 | ---- | 1622 | 75 | 3.6667 | 0.091667 | 0.45833
Subtotal direct job cost | 319027 | 235367 | 17665 | 572059 |  | 3123.6933 | 78.0923 | 390.4617 | Subtotal direct job cost | 233928 | 173919 | 12925 | 420772 |  | 2309.6 | 57.74 | 288.7
Indirect Cost Items
Item Name | Materials | Labor | Equipment | Total
Final Cleanup | 0 | 4405 | 0 | 4405
Insurance | 22081 | 0 | 0 | 22081
Permits & Utilities | 15617 | 0 | 0 | 15617
Design & Engineering | 7265 | 0 | 0 | 7265
Subtotal indirect job cost | 44963 | 4405 | 0 | 49368
Grand Total
Item Name | Materials | Labor | Equipment | Total
Contractor Markup | 80088 | ---- | ---- | 80088
Total cost | 444078 | 239772 | 17665 | 701515
The insurance replacement estimate of this home is $649,647
The cost to replace this home would be $623,133. The cost to demolish the home after a total loss would be $26,514. This is an estimate of the cost to replace the 4,079 square foot single-family residence located at AZ with a building of equal quality, materials, design, layout and workmanship and using methods, techniques and procedures that meet current construction standards. This estimate includes excavation for a foundation on a prepared building pad as required for normal soil condition and utility lines under the building. Costs are current to October, 2017. Replacement is assumed to be done under competitive conditions without significant labor or material shortages.
Characteristics of this home include the following.
The perimeter of the building has 8 corners. The living area is 4,079 square feet. The number of stories is 1. This home was built in 2017 (average age considering all additions). Attic: 549 square feet of finished attic area with more than 78 inch headroom. Attic: 1147 square feet of unfinished attic area with more than 78 inch headroom. Garage: 860 square feet of attached garage under the main building roof, same finish as the home interior. Porch not under the main roof: 922 square feet of porch with open ceiling, shed roof. Concrete deck, walk or driveway: 2162 square feet of surface. Sloping Site: This home is built on sloping ground. The lowest point under the house is 2 feet lower than the highest point. Central ducted heating and cooling. 1 each freestanding wood-burning heat-circulating prefab metal fireplace. This home has fire sprinklers. The quality of this home could be
The quality of this home could be summarized as "Class 4, Good Standard."
Homes of this quality commonly have the following characteristics: Class 4 foundation and floor. Reinforced concrete or concrete block foundation. Conventional wood frame floor or slab on grade. Change in elevation. Class 4 frame exterior walls. Several wall offsets or decorative openings. Several changes in wall height. Class 4 exterior finish. Good stucco or textured siding. Some decorative trim. Class 4 windows and doors. Good quality windows. Decorative entry door. Good grade interior doors. Class 4 roof and soffit. Dual pitch roof with better wood shingles or shakes or concrete tile. 2 foot enclosed soffit. Class 4 interior finish. Textured gypboard or low-cost plaster. Some decorative details or offsets. 9 foot ceilings with spray acoustic texture. Class 4 floor finish. Masonry or tile at entry. Better sheet vinyl or average carpet elsewhere. Class 4 bathrooms. Good plastic tub and shower in master bath. One multi-sink bathroom. Class 4 plumbing and electrical. 3 standard plumbing fixtures per bathroom. Recessed lighting, 6 built-in standard quality appliances. Class 4 kitchen. 15 LF of low cost wall and base cabinets. Low cost tile or acrylic counter top.
The insurance replacement estimates in this report are based on figures which appear in National Building Cost Manual published by Craftsman Book Company, 6058 Corte del Cedro, Carlsbad, CA 92011, 1-800-829-8123, http://www.craftsman-book.com. The sources and methods used to develop this estimate of replacement value reflect changes in the costs of reconstruction and rebuilding, including changes in labor, materials and supplies and are based on a cost index for the Zip area 863 Prescott, Arizona. Index costs for this area are: +3% for material, -16% for labor and +1% for equipment. This estimate assumes a single home is being replaced. October 10, 2017

## House_Est
House Detailed Construction Budget 10-30-17
ITEM NAME | MATERIALS | LABOR | FEES | EQUIPMENT | TOTAL |  | Man Hours | Subtotals | Days
EXCAVATION | [8 empty] | 0
Pad Grading | [6 empty] | 8 |  | 0
Footer Excavation | [6 empty] | 10 |  | 0
Final Grading and Backfill | [6 empty] | 10 |  | 0
0
[8 empty] | 28 | 3.5
HEAVY EQUIPMENT | [8 empty] | 0
Crane Rental x1 week |  |  |  | 2040 |  |  |  |  | 0
0
0
FOUNDATION AND FLATWORK |  |  |  |  | 0 | 46579.1089 |  | 0 | 0
Floor Level 1: Subfloor | 4156.8877 |  |  |  | 4156.8877 |  | 30 |  | 0
Floor Level 2: Subfloor | 2158.7224 |  |  |  | 2158.7224 |  | 10 |  | 0
Floor Level 1: Joists | 7003.311 |  |  |  | 7003.311 |  | 60 |  | 0
Floor Level 2: Joists | 6216.2178 |  |  |  | 6216.2178 |  | 50 |  | 0
Floor Level 2: Beams | 1535.6937 |  |  |  | 1535.6937 |  | 20 |  | 0
Floor Level 2: Hardware | 282.5028 |  |  |  | 282.5028 |  | 4 |  | 0
Floor Level 1: Cripple Wall Need to be treated wood? | 216.8117 |  |  |  | 216.8117 |  | 8 |  | 0
Floor Level 1/2: Rim Board, Blocking, Bracing, & Sill Plate | 2472.8716 |  |  |  | 2472.8716 |  | 30 |  | 0
Floor Level 1: Stem Walls | 4677.1604 |  |  |  | 4677.1604 |  | 60 |  | 0
Floor Level 1: Garage Slab | 4503.4127 | 2400 |  |  | 6903.4127 |  | 20 |  | 0
Porches Slab | 4656.0732 | 2400 |  |  | 7056.0732 |  | 40 |  | 0
Floor Level 1: Footer | 4123.9074 | 1200 |  |  | 5323.9074 |  | 20 |  | 0
Hardware | 439.5707 |  |  |  | 439.5707 |  | 0 |  | 0
Crawlspace | 3035.9658 |  |  |  | 3035.9658 |  | 0 |  | 0
Misc | 1100 |  |  |  | 1100 |  | 30 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
WALLS | [5 empty] | 21488.7913 |  | 382 | 47.75
Exterior Wall Framing | 4493.1854 |  |  |  | 4493.1854 |  | 140 |  | 0
Exterior Wall Sheathing | 4026.788 |  |  |  | 4026.788 |  | 50 |  | 0
Interior Wall Framing | 2711.527 |  |  |  | 2711.527 |  | 60 |  | 0
Posts | 1103.1237 |  |  |  | 1103.1237 |  | 10 |  | 0
Beams | 958.5576 |  |  |  | 958.5576 |  | 20 |  | 0
House Wrap | 655.2874 |  |  |  | 655.2874 |  | 10 |  | 0
Brick Wainscot Siding | -0.0028677 |  |  |  | -0.0028677 |  | 120 |  | 0
Cement Board Siding | 5896.9532 |  |  |  | 5896.9532 |  | 60 |  | 0
Exterior Trim | 1643.3719 |  |  |  | 1643.3719 |  | 30 |  | 0
Exterior Paint → See Finishing | 0 |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  | 0 |  | 0
ROOF | [5 empty] | 50577.122 |  | 500 | 62.5
Roof and Porch Joists | 14578.856 |  |  |  | 14578.856 |  | 90 |  | 0
Roof Sheathing | 7162.6363 |  |  |  | 7162.6363 |  | 40 |  | 0
Roof Underlayment | 1272.2818 |  |  |  | 1272.2818 |  | 6 |  | 0
Metal Roofing | 15805.2389 |  |  |  | 15805.2389 |  | 80 |  | 0
Beams | 9508.1089 |  |  |  | 9508.1089 |  | 30 |  | 0
Hardware | 2250 |  |  |  | 2250 |  | 0 |  | 0
0 | 0 |  |  |  | 0 |  | 0 |  | 0
[5 empty] | 0 |  |  | 246 | 30.75
INSULATION | [5 empty] | 11935.6123 |  |  | 0
Crawlspace Insulation | 1780.1241 |  |  |  | 1780.1241 |  | 8 |  | 0
Exterior Wall Insulation | 2557.5426 |  |  |  | 2557.5426 |  | 25 |  | 0
Roof Insulation | 7597.9456 |  |  |  | 7597.9456 |  | 20 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 53 | 6.625
FINISHING | [5 empty] | 74915.4422 |  |  | 0
Drywall | 8824.4099 |  |  |  | 8824.4099 |  | 120 |  | 0
Flooring | 14296.5215 |  |  |  | 14296.5215 |  | 75 |  | 0
Windows | 6399.437 |  |  |  | 6399.437 |  | 30 |  | 0
Doors | 14610.6568 |  |  |  | 14610.6568 |  | 20 |  | 0
Molding | 918.4635 |  |  |  | 918.4635 |  | 10 |  | 0
Cabinetry / Counter-tops | 18800 |  |  |  | 18800 |  | 20 |  | 0
Sinks Toilets Showers Vanities | 8455 |  |  |  | 8455 |  | 8 |  | 0
0 | 0 |  |  |  | 0 |  | 8 |  | 0
Paint | 2360.9535 |  |  |  | 2360.9535 |  | 120 |  | 0
Misc | 250 |  |  |  | 250 |  | 60 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 471 | 58.875
APPLIANCES BUILT INS | [5 empty] | 12240.1374 |  |  | 0
Clothes Washer (Stackable) | 790.321 |  |  |  | 790.321 |  | 2 |  | 0
Clothes Dryer (Stackable) | 899.8704 |  |  |  | 899.8704 |  | 2 |  | 0
Dishwasher | 976.1638 |  |  |  | 976.1638 |  | 2 |  | 0
Tankless Propane Water Heater | 1305.6054 |  |  |  | 1305.6054 |  | 4 |  | 0
Water Heater Pump & Control | 420.5916 |  |  |  | 420.5916 |  | 1 |  | 0
Gas Range Top | 977.0332 |  |  |  | 977.0332 |  | 4 |  | 0
Electric Double Oven | 1845.3864 |  |  |  | 1845.3864 |  | 4 |  | 0
Wood Stove | 1900.8132 |  |  |  | 1900.8132 |  | 15 |  | 0
Fireplace | 976.1638 |  |  |  | 976.1638 |  | 15 |  | 0
Range Hood | 281.4812 |  |  |  | 281.4812 |  | 2 |  | 0
Water Softener | 1497.0561 |  |  |  | 1497.0561 |  | 4 |  | 0
Water RO System | 556.3981 |  |  |  | 556.3981 |  | 2 |  | 0
Propane Tank | 3000 |  |  |  | 3000 |  | 4 |  | 0
Remove Water Softener | -1497.06 |  |  |  | -1497.06 |  |  |  | 0
[5 empty] | 0 |  |  | 61 | 7.625
HVAC | [5 empty] | 18730 |  |  | 0
HVAC Units | 13230 |  |  |  | 13230 |  | 60 |  | 0
Hydronic Plumbing | 500 |  |  |  | 500 |  | 40 |  | 0
HRV System | 5000 |  |  |  | 5000 |  | 20 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 120 | 15
PLUMBING | [5 empty] | 5192 |  |  | 0
Sewer Plumbing Rough In | 2471 |  |  |  | 2471 |  | 50 |  | 0
Water Pipe Rough In | 2471 |  |  |  | 2471 |  | 40 |  | 0
Gas Pipe Rough In | 250 |  |  |  | 250 |  | 10 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 100 | 12.5
ELECTRIC | [5 empty] | 9481 |  |  | 0
Electric | 9481 |  |  |  | 9481 |  | 95 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 95 | 11.875
FIRE SPRINKLERS | [5 empty] | 10330 |  |  | 0
Fire Sprinklers | 10330 |  |  |  | 10330 |  | 0 |  | 0
0 | 0 |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 0 | 0
OUTSOURCES LABOR | [5 empty] | 4800 |  |  | 0
General help for standing walls, roofing and misc |  | 4800 |  |  | 4800 |  |  |  | 0
160 hours @ $30/hr |  |  |  |  | 0 |  |  |  | 0
[5 empty] | 0 |  |  | 0 | 0
TOTAL | 263158.9009 | 10800 | 0 | 0 | 273958.9009 | 266269.2141 | 2056 | 2056 | 257

## Shop_Est
Shop Detailed Construction Budget 10-30-17
Item Name | Materials | Outsource Labor | Fees | Equipment | Total |  |  |  | Shop Dimensions
Shop | [6 empty] | Man Hours | Subtotals |  |  | x | y
Pad Clearing and Footer Excavation |  |  |  |  | 0 |  | 10 |  | Wall ID | Length (ft) | 34 | 0
https://www.versatube.com/design-your-own?id=169501 | 34487.2 |  |  |  | 34487.2 |  | 120 |  | W1 | 34 | 0 | 0
Footer Concrete | 712.8603 |  |  |  | 712.8603 |  | 10 |  | W2 | 54 | 0 | 54
Slab Concrete | 4249.388 | 2400 |  |  | 6649.388 |  | 10 |  | W3 | 34
Slab/Footer ABC Fill @ 4” Thick | 910.2189 |  |  |  | 910.2189 |  | 10 |  | W4 | 54
Footer Rebar | 279.9719 |  |  |  | 279.9719 |  | 2 |  | L1 | 12
Slab Rebar | 1375.4708 |  |  |  | 1375.4708 |  | 10 |  | L2 | 54
Insulation Walls | 1445.944 |  |  |  | 1445.944 |  | 20 |  | L3 | 12
Insulation Roof | 3963.2677 |  |  |  | 3963.2677 |  | 20 |  | L4 | 54
Insulation Misc | 100 |  |  |  | 100 |  | 4 |  | Apartment Int Wall Length | 116
Two (4) Man Doors | 704.2464 |  |  |  | 704.2464 |  | 4 |  | Exterior Wall Height (ft) | 16
Two (2) 10'x10' Doors | 1682.3664 |  |  |  | 1682.3664 |  | 4 |  | Slab Thickness (ft) | 0.5
One (1) 10'x14' Door | 1086.8 |  |  |  | 1086.8 |  | 2 |  | Slab/Footer Fill Thickness (ft) | 0.33333
Six (6) 2'x2' Windows | 308.8251 |  |  |  | 308.8251 |  | 8 |  | Footer Width (ft) | 1
Shop Inside Wall Studs | 393.7433 | -393.7433 |  |  | 0 |  | 16 |  | Footer Height (ft) | 0.5
Shop Inside Wall Top/Bottom Plate | 196.8716 | -196.8716 |  |  | 0 |  |  |  | Exterior Wall Length (w/o lean to) (ft) | 176
Drywall Shop Main Walls | 510.7091 | -510.7091 |  |  | 0 |  | 20 |  | Slab Floor Area (ft^2) | 1836
Electrical and Lights | 1000 |  |  |  | 1000 |  | 40 |  | Insulated Wall Area (ft^2) | 2816
[5 empty] | 0 |  |  |  | Insulated Roof Area (ft^2) | 1893
[5 empty] | 0 |  |  |  | Insulated Area (ft^2) | 4709
[5 empty] | 0 | 54706.5594 |  | 310 | Footer Concrete Volume (yd^3) | 5.7037
Apartment |  |  |  |  | 0 |  |  |  | Footer Rebar Length (ft) | 616
Apartment: Wall Studs | 352.2993 |  |  |  | 352.2993 |  | 40 |  | Slab/Footer Fill Volume (ft^3) | 612
Top/Bottom Plate | 264.2244 |  |  |  | 264.2244 |  |  |  | Slab Concrete Volume (yd^3) | 34
Drywall | 774.1885 |  |  |  | 774.1885 |  | 40 |  | Slab Rebar length (ft) | 3157.92
2nd Floor Truss 2x12 @ 24” o.c | 319.5192 |  |  |  | 319.5192 |  | 4 |  | Cost / ft^2 | 36.8414
2nd Floor Plywood Subfloor | 531.1579 |  |  |  | 531.1579 |  | 4
Apartment Stairs | 225 |  |  |  | 225 |  | 4
Nails & Screws | 100 |  |  |  | 100
Lighting Fixtures | 300 |  |  |  | 300 |  | 8
Paint | 200 |  |  |  | 200 |  | 8
Flooring | 150 |  |  |  | 150 |  | 8
Bath Accessories | 200 |  |  |  | 200 |  | 16
stair | 420.5916 |  |  |  | 420.5916 |  | 8
Plumbing Fixtures | 600 |  |  |  | 600 |  | 16
Plumbing Rough-in | 750 |  |  |  | 750 |  | 16
Wiring | 1009 |  |  |  | 1009 |  | 10
Built In Appliances | 1200 |  |  |  | 1200 |  | 8
Cabinets | 250 |  |  |  | 250 |  | 8
Countertops | 300 |  |  |  | 300 |  | 8
Interior Doors | 247.6274 |  |  |  | 247.6274 |  | 8
3 Zone Mini-Split | 2500 | 500 |  |  | 3000 |  | 20
Sewage Pump | 447.5551 |  |  |  | 447.5551
Misc |  |  |  |  | 0 |  | 10
Porta Potty Rental During Building | 500 |  |  |  | 500
Scissor lift rental x2 weeks |  |  |  | 693 | 693
Other | 100 |  |  |  | 100
0
[5 empty] | 0 | 12934.1634 |  | 244
Total | 65149.0468 | 1798.676 | 0 | 693 | 67640.7228 |  | 554 | 554
67640.7228
33153.5228

## Dimensions_Calcs
Exterior Walls
|  | x | y
Wall ID | Length (ft) | 96 | 0
L1 | 96 | 0 | 0
L2 | 52 | 0 | 52
L3 | 32 | 32 | 52
L4 | 16 | 32 | 36
L5 | 32 | 64 | 36
L6 | 16 | 64 | 52
L7 | 32 | 96 | 52
L8 | 52 | 96 | 0
Exterior Wall Height (ft) | 8
Exterior Wall Length(ft) | 328
Total Area (ft^2) | 4480
Garage Area (ft^2) | 860.1
Finished Area (ft^2) | 3619.9
Exterior Wall Area (ft^2) | 2624
Doors
Front Door | 1 | Baseboard | 334
Exterior Doors | 4 | Door Trim | 1400
Interior Doors | 35 | Door Frame
Sliding Door | 1
Windows
Window Large | 4
Window Medium | 12
Window Small | 6 |  |  | Gross Floor Areas | [7 empty] | LOT SIZE AND ZONING REQUIREMENTS FOR R1l-70
|  |  |  | Room | Area | Percent of Total Conditioned Space | BTU Loss | Heat BTU | Cool BTU | Mech. Vent. CFM |  |  | ZONING REQ | HOUSE | SHOP | TOTAL
|  |  |  | Master Bed E | 324.3 | 7.373% | 44.9741 | 2023.8337 | 1798.9633 | 7.7414 |  | PROPOSED BUILDING GROUND AREA (S.F.) | - | 4480 | 2484 | 6964
|  |  |  | Master Bed E Bath | 128.9 | 2.93% | 17.8759 | 804.4162 | 715.0366 | 3.077 |  | ACTUAL LOT AREA (S.F.) | - | - | - | 186279
Bathrooms |  |  |  | Master Bed E Closet | 63.1 | 1.435% | 8.7507 | 393.7832 | 350.0296 | 1.5063 | 12.3247 | MIN LOT SIZE (S.F) | 70000 | - | - | -
Vanity Single | 2 |  |  | Master Bed W | 401.8 | 9.135% | 55.7218 | 2507.4819 | 2228.8728 | 9.5915 |  | MIN AREA PER DWELLING (S.F.) | 70000 | - | - | -
Vanity Double | 2 |  |  | Master Bed W Bath | 114.6 | 2.605% | 15.8928 | 715.1753 | 635.7114 | 2.7356 | 14.2798 | MIN LOT WIDTH AND DEPTH (FT) | 200 | - | - | -
Vanity Sink Single | 2 |  |  | Bedroom 1 | 200.8 | 4.565% | 27.847 | 1253.1169 | 1113.8817 | 4.7933 | 6.641 | MIN YARD SETBACK FRONT (FT) | 50 | 50 | 50 | -
Vanity Sink Double | 2 |  |  | Bedroom 2 | 269.7 | 6.131% | 37.4021 | 1683.0958 | 1496.0851 | 6.4381 | 8.2857 | MIN YARD SETBACK REAR (FT) | 50 | 50 | 50 | -
Toilet | 3 |  |  | Bedroom 3 | 216 | 4.911% | 29.955 | 1347.9744 | 1198.1994 | 5.1562 | 7.0038 | MIN YARD SETBACK INTERIOR (FT) | 25 | 25 | 25 | -
Kitchen Sink | 2 |  |  | Study | 289.3 | 6.577% | 40.1203 | 1805.4119 | 1604.8106 | 6.9059 | 8.7536 | MIN YARD SETBACK EXTERIOR (FT) | 30 | 30 | 30 | -
Shower Fixture | 2 |  |  | Bathroom | 137 | 3.115% | 18.9992 | 854.9652 | 759.9691 | 3.2704 |  | MAX BUILDING HEIGHT STORIES | 2 | 1.5 | 1.5 | -
Medicine Cabinet | 6 |  |  | Hallway 1 | 95.2 | 2.164% | 13.2024 | 594.1072 | 528.0953 | 2.2725 |  | MAX BUILDING HEIGHT (FT) | 30 | 23 | 21 | -
Mirror | 6 |  |  | Hallway 2 | 81.8 | 1.86% | 11.3441 | 510.4829 | 453.7626 | 1.9527 |  | MAX LOT COVERED (5) | 15 | 2.405% | 1.333% | 3.738%
Bathtub | 2 | [8 empty] | 0 |  | MIN BUILDING SPACING (FT) | 3 | - | - | -
Clothes Washer | 2 | [8 empty] | 0
Dishwasher | 2 |  |  | Living Room | 513.7 | 11.68% | 71.2402 | 3205.8075 | 2849.6067 | 12.2627
|  |  |  | Kitchen | 273.2 | 6.211% | 37.8875 | 1704.9379 | 1515.5004 | 6.5216
|  |  |  | Dining Room | 249.5 | 5.672% | 34.6008 | 1557.0352 | 1384.0313 | 5.9559
|  |  |  | Foyer | 129.7 | 2.949% | 17.9869 | 809.4087 | 719.4744 | 3.0961
Master Bath | 9 |  |  | Utility | 69.7 | 1.585% | 9.666 | 434.9714 | 386.6412 | 1.6638
Guest Maser Bath | 9 |  |  | Spare Bath | 61.7 | 1.403% | 8.5566 | 385.0464 | 342.2634 | 1.4729 | 64.987
Bedroom Bath | 9 |  |  | Total 1st floor | 3620 |  |  |  |  | 0
Laundry Bath | 7 | [8 empty] | 0
Kitchen Sink | 2 |  |  | Loft (finished) | 778.6 | 17.7% | 107.9766 | 4858.9483 | 4319.0652 | 18.5861
Dishwasher | 2 |  |  | Bonus Room East (unfinished) | 501.2 | 11.39% | 69.5067 | 3127.7998 | 2780.2664 | 11.9643 | 11.9643
Laundry Room Sink |  |  |  | Bonus Room West (unfinished) | 646.3 | 14.69% | 89.6292 | 4033.314 | 3585.168 | 15.428
Shop | 7 |  |  | Total 2nd floor | 1926.1 |  |  |  |  | 0
[6 empty] | 126.1% | 769.1359 | 34611.1138 | 30765.4345 | 132.3922 | 134.2399
|  |  |  | Total Finished Floor Area | 4398.6
|  |  |  | Garage | 860.1
|  |  |  | Total Gross Floor Area w/o Garage | 5546.1
|  |  |  | Total Gross Floor Area w/ Garage | 6406.2
|  |  |  | Total Gross Roof Area w/ Porches and Overhangs | 5793.6
1147.5

## Flatwork_Calcs
Test Scenarios
Flatwork Budget Calcs | [6 empty] | Category | Cost | 2'X10' #2 Doug Fir |  |  |  | Pricing
Floor Level 1: Subfloor | [5 empty] | 1 | Floor Level 1: Subfloor | 4156.8877 | Full Span (ft) | 38 | Joist length (ft) | 14 | Foxworth Glabrath
Rooms | Material | Size | Area (ft^2) | Price/ft^2 | Total | 2 | Floor Level 2: Subfloor | 2158.7224 | Length (ft) | 96 | Joist $/ft | 1.2962 | 928-445-2525
Main | 7/8” T&G Plywood | 73'x36' | 2628 | 1.0997 | 2890.0267 | 3 | Floor Level 1: Joists | 7003.311 | OC (ft) | 1.3333 | Joist Material $ | 3919.86 | talked to Tony on 2/10/17
Master Bd 1 | 7/8” T&G Plywood | 16'x36' | 576 | 1.0997 | 633.4305 | 4 | Floor Level 2: Joists | 6216.2178 | # girders | 2 |  |  | carries Boise Cascade TJIs
Master Bd 2 | 7/8” T&G Plywood | 35.7395 | 576 | 1.0997 | 633.4305 | 5 | Floor Level 2: Beams | 1535.6937 | # joists deep | 3 |  |  | Joist |  | $/ft
Total |  |  |  |  | 4156.8877 | 6 | Floor Level 2: Hardware | 282.5028 | # joists across | 72 |  |  | 2x10 | $20.74/16' | 1.2962
Floor Level 2: Subfloor | [5 empty] | 7 | Floor Level 1: Cripple Wall Need to be treated wood? | 216.8117 | Joist Span (ft) | 12.6667 |  |  | 2x12 |  | 1.6
Rooms | Material | Size | Area (ft^2) | Price/ft^2 | Total | 8 | Floor Level 1/2: Rim Board, Blocking, Bracing, & Sill Plate | 2472.8716 | # joist total | 216 |  |  | 9 ½ TJI
Loft Main | 7/8” T&G Plywood | 15.5'x42' | 651 | 1.0997 | 715.9084 | 9 | Floor Level 1: Stem Walls | 4677.1604 |  |  |  |  | 11 7/8 TJI |  | 2.45
Loft Side 1 | 7/8” T&G Plywood | 4'x20' | 80 | 1.0997 | 87.9765 | 10 | Floor Level 1: Garage Slab | 4503.4127
Loft Side 2 | 7/8” T&G Plywood | 4'x20' | 80 | 1.0997 | 87.9765 | 11 | Porches Slab | 4656.0732
East Bonus Rm | 7/8” T&G Plywood | 16'x36' | 576 | 1.0997 | 633.4305 | 12 | Floor Level 1: Footer | 4123.9074
West Bonus Rm | 7/8” T&G Plywood | 35.7395 | 576 | 1.0997 | 633.4305 | 13 | Hardware | 439.5707 | 9 1/2” TJI |  |  |  | Pricing
Total |  |  |  |  | 2158.7224 | 14 | Crawlspace | 3035.9658 | Full Span (ft) | 38 | Joist length (ft) | 12.5 | www.menards.com
Floor Level 1: Joists | [5 empty] | 15 | Misc | 1100 | Length (ft) | 96 | Joist $/ft | 1.49
Row | Size | Length (ft) | # each | Price/ft | Total |  |  |  | OC (ft) | 1.3333 | Joist Material $ | 4023
J1A | 11-7/8” TJI 360 | 16 | 23 | 2.6627 | 979.8589 |  | Total | 46579.1089 | # girders | 2
J2B | 11-7/8” TJI 360 | 16 | 23 | 2.6627 | 979.8589 |  |  |  | # joists deep | 3 |  |  | Joist |  | $/ft
J3 | 11-7/8” TJI 360 | 35.7395 | 53 | 2.6627 | 5043.5933 |  |  |  | # joists across | 72
Total |  |  |  |  | 7003.311 |  |  |  | Joist Span (ft) | 12.6667
Floor Level 2: Joists | [8 empty] | # joist total | 216 |  |  | 9 ½ TJI | $23.84/16' | 1.49
Row | Size | Length (ft) | # each | Price/ft | Total
J4 | 3x12 rough sawn #2 df | 21.3125 | 4 | 3.5104 | 299.2585
J5A | 3x12 rough sawn #2 df | 18.5 | 4 | 3.5104 | 259.7669
J5B | 11−7/8" TJI 110 | 17.5781 | 13 | 2.6627 | 608.4594
J6 | 11−7/8" TJI 110 | 17.5781 | 13 | 2.6627 | 608.4594 |  |  |  | 11 7/8” TJI
J7 | 3x12 rough sawn #2 df | 36 | 23 | 3.5104 | 2906.5814 |  |  |  | Full Span (ft) | 38 | Joist length (ft) | 12.5
J8 | 11−7/8" TJI 110 | 36 | 16 | 2.6627 | 1533.6922 |  |  |  | Length (ft) | 96 | Joist $/ft | 0
Total |  |  |  |  | 6216.2178 |  |  |  | OC (ft) | 2 | Joist Material $ | #VALUE!
Floor Level 2: Beams
Row | Size |  | Length (ft) | Price/ft | Total
B1 | 5 1/2" x 16 1/2" glulam, 22' 10" |  | 22.8333 | 35.2667 | 805.2554
B2 | 3 1/2" x 21" glulam, 25' 5 1/2" span |  | 25.4583 | 28.6915 | 730.4383
Total |  |  |  |  | 1535.6937
Floor Level 2: Hardware
Joists | Item |  | # | Price/ea | Total
J4 | Simpson IUS1.81/11.8 |  | 26 | 5.3145 | 138.1758
J5 | Simpson U210R |  | 4 | 4.5102 | 18.0409
J6 | Simpson U210R |  | 5 | 4.5102 | 22.5511
J7 | Simpson U210R |  | 23 | 4.5102 | 103.7351
Total |  |  |  |  | 282.5028
Floor Level 1: Cripple Wall Need to be treated wood? | [8 empty] | # girders | 2
Row | Size | Length | # ft | Price/ft | Total |  |  |  | # joists deep | 3
1 | 2x4 | 72 | 360 | 0.48634 | 175.0835 |  |  |  | # joists across | 48
2 | 2x4 | 31 | 68.2 | 0.48634 | 33.1686 |  |  |  | Joist Span (ft) | 12.6667
3 | 2x4 | 8 | 17.6 | 0.48634 | 8.5596 |  |  |  | # joist total | 144
Total |  |  |  |  | 216.8117
Floor Level 1/2: Rim Board, Blocking, Bracing, & Sill Plate
Item | Size | Length | # ft | Price/ft | Total
Rim board | 1.125x11 7/8 | 296 | 296 | 2.1736 | 643.3856
Blocking | 1.125x11 7/8 | 448 | 448 | 2.1736 | 973.7728
Sill Plate(s) | 2x4 (treated) | 268 | 268 | 0.78087 | 209.272
Sill Plate(s) | 2x6 (treated) | 89 | 89 | 1.1558 | 102.8673
Bracing | 2x4 | 416 | 416 | 0.48634 | 202.3187
2nd Floor Blocking | 1.125x11 7/8 | 157 | 157 | 2.1736 | 341.2552
Total |  |  |  |  | 2472.8716
Floor Level 1: Stem Walls
Item | Material | Length | # | Price/# | Total
Stem Wall Block | 8x8x16 CMU | 328 | 918.4 | 1.3042 | 1197.7405
Concrete Fill | Concrete |  | 16.5 | 108.68 | 1793.22
Bond Beam | #4 Rebar | 328 | 721.6 | 0.37875 | 273.3059
Vertical Rebar | #4 Rebar | 82 | 430.5 | 0.37875 | 163.0518
Surface Bonding C | Quickwall | 328 | 2755.2 | 0.45363 | 1249.8423
Total |  |  |  |  | 4677.1604
Floor Level 1: Garage Slab
Item | Size | Thickness | # yd^3 / ft^3 | Price/unit | Total
Int Pad Concrete | 840 | 0.41667 | 14.9074 | 108.68 | 1620.137
Ext Pad Concrete | 782 | 0.41667 | 13.8781 | 108.68 | 1508.2704
ABC Fill | 1622 | 0.33333 | 540.6667 | 1.2933 | 699.2399
Int Pad Rebar | #4 Rebar 24” o.c. units in length → |  | 924 | 0.37875 | 349.9648
Ext Pad Rebar | #4 Rebar 24” o.c. units in length → |  | 860.2 | 0.37875 | 325.8006
Total |  |  |  |  | 4503.4127
Porches Slab
Item | Size | Thickness | # yd^3 | Price/ft | Total
Front Patio Concrete | 196 | 0.33333 | 2.7827 | 108.68 | 302.4256
Rear Patio Concrete | 1184 | 0.33333 | 16.8099 | 108.68 | 1826.8974
ABC Fill | 1380 | 0.33333 | 460 | 1.2933 | 594.9143
Front Patio Rebar | #4 Rebar 24” o.c. units in length → |  | 215.6 | 0.66023 | 142.3458
Back Patio Rebar | #4 Rebar 24” o.c. units in length → |  | 2710.4 | 0.66023 | 1789.4901
Total |  |  |  |  | 4656.0732
Floor Level 1: Footer
Row | CS Size (ft^2) | Length (ft) | # yd^3 /ft^3 / ft | Price/yd^3 | Total
Ext Walls Conc. | 2 | 328 | 27.9407 | 108.68 | 3036.5997
Int Walls (garage) Conc. | 2 | 60 | 5.1111 | 108.68 | 555.4756
Footer ABC Fill |  | 0.33333 | 76.0193 | 1.2933 | 98.3151
Ext Wall Rebar | #4 Rebar units in length → |  | 967.6 | 0.37875 | 366.4783
Int Wall Rebar | #4 Rebar units in length → |  | 177 | 0.37875 | 67.0387
Total |  |  |  |  | 4123.9074
Hardware
Item | - | - | # | Price/# | Total
J-Bolts | J-Bolts | 88 | 2 | 86.9223 | 173.8445
Joists | 10d nails | 99 | 792 | 0.013838 | 10.9594
Rim board | 10d nails | 0 | 0 | 0.013838 | 0
Blocking | 10d nails | 0 | 0 | 0.013838 | 0
Sub Floor Glue | Sub Floor Glue | - | 2630.1935 | 0.055363 | 145.6151
Sub Floor Nails | 6d ring or screw shank, or 8d common | 113 | 3944 | 0.013838 | 54.5758
Sub Floor Nails | 6d ring or screw shank, or 8d common | 113 | 3944 | 0.013838 | 54.5758
Hold Downs | Sheer Wall Hold Downs
Total |  |  |  |  | 439.5707
Crawlspace
Item | Material | Length | Area (ft^2) | Price/unit | Total
Vapor Barrier | Class 1 Vapor Retarder |  | 4928 | 0.51707 | 2548.1012
Vapor Barrier Tape | Vapor Barrier Tape | 9.856 | 10 | 35.8535 | 358.5353
Mech Ventilator | Crawl Space Ventilator |  | 1 | 129.3292 | 129.3292
Total |  |  |  |  | 3035.9658
Misc
Item | Material | Length | Area (ft^2) | Price/unit | Total
Staircase |  |  |  |  | 500
Staircase Railing |  |  |  |  | 300
Balcony Railing |  |  |  |  | 300
Total |  |  |  |  | 1100
Total |  |  |  |  | 46579.1089

## Wall_Calcs
Wall Calcs | [6 empty] | Category | Cost
Exterior Wall Framing | [6 empty] | Exterior Wall Framing | 4493.1854
Material | Wall L. (ft) | Board L. (ft) | # / ft | Price/each | Total |  | Exterior Wall Sheathing | 4026.788
2x4 Stud | 269 | 8 | 322.8 | 3.8907 | 1255.9322 |  | Interior Wall Framing | 2711.527
2x4 T/B Plate | 269 | 8 | 161.4 | 3.8907 | 627.9661 |  | Posts | 1103.1237
2x4 King Stud | 15 | 8 | 33 | 3.8907 | 128.3946 |  | Beams | 958.5576
2x4 Cripple Stud | 15 | 8 | 16.5 | 3.8907 | 64.1973 |  | House Wrap | 655.2874
2x12 Header | 15 | 8 | 132 | 11.7374 | 1549.3421 |  | Brick Wainscot Siding | -0.0028677
2x6 Stud | 30 | 10 | 18 | 8.5096 | 153.1736 |  | Cement Board Siding | 5896.9532
2x6 T/B Plate | 30 | 10 | 7.2 | 8.5096 | 61.2694 |  | Exterior Trim | 1643.3719
Ply Fire Block | 269 | 8 | 9.2469 | 35.1906 | 325.4029 |  | Exterior Paint → See Finishing | 0
Nails |  |  | 5601.175 | 0.013838 | 77.5073
Calking/Sealing Foam |  |  |  |  | 250 |  | Total | 21488.7913
Total |  |  |  |  | 4493.1854
Exterior Wall Sheathing
Material | Wall L. (ft) | ft per 4x8sheet | # Sheets | Price/each | Total
19/32 Ply | 400 | 4 | 115 | 27.5504 | 3168.2937
19/32 Ply | 400 | 16 | 28.75 | 27.5504 | 792.0734
Nails | 400 |  | 4800 | 0.013838 | 66.4209
Total |  |  |  |  | 4026.788
Interior Wall Framing
Material | Wall L. (ft) / # op. | Board L. (ft) | # | Price/each | Total
2x4 Stud | 484 | 8 | 326.7 | 3.8907 | 1271.1061
2x4 King Stud | 22 | 8 | 50.6 | 3.8907 | 196.8716
2x4 Header | 22 | 8 | 12.65 | 5.2818 | 66.8154
2x4 T/B Plate | 484 | 8 | 139.15 | 3.8907 | 541.397
2x6 Stud | 66 | 8 | 41.25 | 5.2818 | 217.8762
2x6 Header | 3 | 8 | 1.725 | 5.2818 | 9.1112
2x6 T/B Plate | 66 | 8 | 18.975 | 5.2818 | 100.2231
Ply Fire Block | 550 | 80 | 6.875 | 35.1906 | 241.9353
Nails |  |  | 4783.4 | 0.013838 | 66.1912
Total |  |  |  |  | 2711.527
Posts
ID | MATERIAL | LENGTH | # | Price/each | Total
C1-C4 | 6x6 post | 10 | 4 | 3.6408 | 145.6312
C5-C15 | 6x6 post | 10 | 40 | 0.48634 | 194.5372
C16, C17 | stem wall | 4 | 8 | 0.48634 | 15.563
C18-20 | 6x6 post. | 10 | 12 | 0.48634 | 58.3612
C21-24 | stem wall | 10 | 4 | 3.6408 | 145.6312
C12 | 7x7 paralam | 25 | 1 | 21.736 | 543.4
Total |  |  |  |  | 1103.1237
Beams
ID | Material |  | # | Price/each | Total
B1 | 5 1/2" x 16 1/2" glulam |  | 23 | 19.5624 | 449.9352
B2 | 3 1/2" x 21" glulam |  | 26 | 19.5624 | 508.6224
Total |  |  |  |  | 958.5576
House Wrap
Material | Wall L. (ft) | Wall Height (ft) | Area (ft^2) | Price/ft^2 | Total
Tyvek | 400 | 9 | 4140 | 0.13283 | 549.9208
Tyvek Tap | 400 | Length → | 1200 | 0.087805 | 105.3666
Total |  |  |  |  | 655.2874
Brick Wainscot Siding
Material | Wall L. (ft) | # High | # Total | Price/each | Total
CMU | 96 | 2 | 144 | 1.7932 | 258.2237
Brick | 96 | 24 | 3456 | 0.70642 | 2441.3875
Morter |  |  | 25.92 | 12.3352 | 319.7279
Sand |  |  | 12 | 17.3888 | 208.6656
Brick Ties | 96 | 36 | 172.8 | 0.17139 | 29.6159
Top Flashing | 96 |  | 110.4 | 1.3661 | 150.8183
Bottom Flashing | 96 |  | 110.4 | 1.3661 | 150.8183
Remove Brick Siding |  |  |  |  | -3559.26
Total |  |  |  |  | -0.0028677
Cement Board Siding
Material | Wall L. (ft) | ft High | # Units | Price/unit | Total
Cement Board | 400 | 9 | 4140 | 1.3538 | 5604.9071
Nails | 400 | 9 | 8640 | 0.0048664 | 42.0461
Calking |  |  |  |  | 250
Total |  |  |  |  | 5896.9532
Exterior Trim
Material | # | ft length each | ft total | Price/unit | Total
Bld Corners | 8 | 9 | 144 | 1.2362 | 178.0178
Man Doors | 4 | 18 | 144 | 1.2362 | 178.0178
Sliding Door | 1 | 26 | 52 | 1.2362 | 64.2842
Garage Door | 1 | 50 | 100 | 1.2362 | 123.6235
Windows | 16 | 24 | 768 | 1.2362 | 949.4285
Nails |  |  |  |  | 50
Caulking |  |  |  |  | 100
Total |  |  |  |  | 1643.3719
Exterior Paint → See Finishing
Material |  |  |  | Price/unit | Total
Paint → See Finishing |  |  |  | 0 | 0
Total |  |  |  |  | 0
Total |  |  |  |  | 21488.7913
Braced Wall Calculations
wall # | Ceiling Height | opening height adjacent to Braced wall | type(s) of Braced wall Panel | distance between braced walls | required total feet of bracing | provided total Feet bracing | notes
A 1-2 | 9' |  | WSP | 28'-5” | 11.2' | 21'-4”
A 2-4 | 8' |  | WSP | 38'-7” | 15.3' | 17'-4”
A 4-5 | 8' |  | WSP | 28'-11” | 11.2' | 20'-5”
B 1-2 | 8' |  | GB | 28'-5” | 19.3' | 17'-4”
B 2-4 | 8' |  | WSP | 38'-10” | 12.2' | 14'-0”
B 4-5 | 8' |  | GB | 28'-11” | 19.3' | 26'-5”
C 1-2 | 8' |  | WSP | 28'-5” | 11.2' | 20'-2”
D 3-5 | 8' |  | WSP | 31'-2” | 12' | 12'7”
1 A-B | 8' |  | PFG | 36'-1” | 15.3' | 17.9
1 B-C | 8' |  | WSP | 15'-11” | 8.1' | 15'-11”
2 A-B | 9' |  | GB | 36'-1” | 21.8' * | 25'-0”
2 B-C | 8' |  | WSP | 15'-11” | 8.1' | 15'-11”
3 B-D | 8' |  | WSP | 15'-11” | 8.1' | 15'-11”
4 A-B | 8' |  | GB | 36'-1” | 25.4' | 30'-7”
5 A-B | 8' |  | WSP | 36'-1” | 15.3' | 22'-3”
5 B-C | 8' |  | WSP | 15'-11” | 8.1' | 11'-0”
Braced Wall Spacing per IRC 2012
IRC 2012 Table #
Braced Wall Line Spacing (ft) | R602.10.3(1) | R602.10.3(2) | R602.10.3(2) | R602.10.3(2) | R602.10.3(2) | R602.10.3(2) | R602.10.3(2) | R602.10.3(2) | Final (ft)
| Base | Exp | Eave | Height | # BWL | Hold Dwn | Int GWB | GWB Fst
GB
10 | 3.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 7.1253
20 | 7 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 14.2506
30 | 9.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 19.3401
40 | 12.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 25.4475
50 | 15.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 31.5549
60 | 18.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 37.6623
WSP
10 | 2 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 4.0716
20 | 4 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 8.1432
30 | 5.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 11.1969 | 4.0716
40 | 7.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 15.2685 | 0.40716
50 | 9 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 18.3222 | 2.4837
60 | 10.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 21.3759 | 21.7837
CS-WSP
10 | 2 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 4.0716
20 | 3.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 7.1253
30 | 5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 10.179
40 | 6 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 12.2148
50 | 7.5 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 15.2685
60 | 9 | 1.2 | 1.3 | 0.9 | 1.45 | 1 | 1 | 1 | 18.3222

## Roof_Calcs
Roof | [7 empty] | Category | Cost
Roof and Porch Joists | [7 empty] | Roof and Porch Joists | 14578.856
Joist | Member | Length | Quantity | Units | Price/unit | Total |  | Roof Sheathing | 7162.6363
J8a,b | pre−fab scissor truss @ 24" o.c. | 32’ / 35’ 9" overal |  |  |  | 4474 |  | Roof Underlayment | 1272.2818
J9a,b | 14" TJI 110 @ 24" o.c. | 17 | 16 | 312.8 | 2.8257 | 883.8727 |  | Metal Roofing | 15805.2389
J10a,b | 2x10 lumbervalley set @ 24" o.c. | various |  | 115 | 1.2652 | 145.4999 |  | Beams | 9508.1089
J11a,b,c,d | 14" TJI 110 @ 24" o.c. | various | 36 | 351.9 | 2.8257 | 994.3568 |  | Hardware | 2250
J12a,b | 14" TJI 110 @ 24" o.c. | 18’ 0" add 8:12 slope | 30 | 690 | 2.8257 | 1949.7192
J13a,b,c,d | 14" TJI 110 @ 24" o.c. | various | 32 | 312.8 | 2.8257 | 883.8727 |  | Total | 50577.122
J14a,b,c,d | 14" TJI 110 @ 24" o.c. | 18’ 0" add 8:12 slope | 30 | 690 | 2.8257 | 1949.7192
J15a,b | 2x6 #2 df @ 24" o.c. | various | 8 | 32.2 | 0.85096 | 27.4011
J16a,b | 2x6 #2 df @ 24" o.c. | various | 18 | 165.6 | 0.85096 | 140.9197
Front Porch Hip | 2x6 DF |  | 4 | 55.2 | 0.85096 | 46.9732
Front Porch Nailer | 2x6 DF |  |  | 40.25 | 0.85096 | 34.2513
Outriggers | 2x4 DF | 4 | 76 | 349.6 | 0.48634 | 170.0255
Soffit Support | 2x4 DF | 3 | 32 | 110.4 | 0.48634 | 53.6923
Soffit Sheeting | Cement Board Soffit Covering |  |  | 818.8 | 1.8842 | 1542.8153
Porch Cedar Ceiling | T&G Cedar |  |  | 303.6 | 2.8764 | 873.2742
Facia | 2x6 DF |  |  | 480 | 0.85096 | 408.4629
Total | [5 empty] | 14578.856
Roof Sheathing
Material | Material |  | Area (ft(s) |  | Price/unit | Total | 0.625
19/32 Plywood | Main Gable |  | 5252.05 |  | 0.86095 | 4521.7492 | 0.71875
19/32 Plywood | Porches |  | 1092.5 |  | 0.86095 | 940.5872 | 0.59375
19/32 Plywood | Mstr Bed #1 |  | 741.75 |  | 0.86095 | 638.6092
19/32 Plywood | Mstr Bed #2 |  | 741.75 |  | 0.86095 | 638.6092
Nails | Roofing Nail |  | 7828.05 |  | 0.0048664 | 38.0948
Clips for Sheathing | Roof Sheathing |  | 2250.5644 |  | 0.17106 | 384.9868
Total | [5 empty] | 7162.6363
Roof Underlayment
Material | Material |  | Area (ft(s) |  | Price/unit | Total
UDL Titanium 50 | Main Gable |  | 4567 |  | 0.18691 | 853.6082
UDL Titanium 50 | Porches |  | 950 |  | 0.18691 | 177.5625
UDL Titanium 50 | Mstr Bed #1 |  | 645 |  | 0.18691 | 120.5556
UDL Titanium 50 | Mstr Bed #2 |  | 645 |  | 0.18691 | 120.5556
Total | [5 empty] | 1272.2818
Metal Roofing
Material | Material |  | Area (ft(s) |  | Price/unit | Total
Metal Roofing | Main Gable |  | 4567 |  | 2.1736 | 9926.8312
Metal Roofing | Porches |  | 950 |  | 2.1736 | 2064.92
Metal Roofing | Mstr Bed #1 |  | 645 |  | 2.1736 | 1401.972
Metal Roofing | Mstr Bed #2 |  | 645 |  | 2.1736 | 1401.972
Vent Boot | Boots |  | 3 |  | 15 | 45
Facia Metal Covering |  | Length → | 534 |  | 0.90313 | 482.2718
Drip Edge |  | Length → | 534 |  | 0.90313 | 482.2718
Total | [5 empty] | 15805.2389
Beams
ITEM | MATERIAL | LENGTH(FT) | # | Total Units | Price/Unit | Total
B3a,b,c,d | 6x6 rough sawn df | 5.5 | 4 | 22 | 3.6408 | 80.0972
B4a,b | 3 5/8” x 14” glulam | 19 | 2 | 38 | 23.3119 | 885.8507
B5a,b | 6x6 rough sawn df | 5 | 2 | 10 | 3.6408 | 36.4078
B6 | 3.5"x18" 24F−V8 DF Glulam | 49.2 | 1 | 49.2 | 28.6915 | 1411.6228
B7a,b,c,d | 1.75”(x3) x 16” LVL | 29 | 12 | 348 | 8.2379 | 2866.8045
B8 | 5.5"x24" 24F-V4 DF Glulam | 23.3 | 1 | 23.3 | 32.604 | 759.6732
B9 | 6.75"x24" 24F-V4 DF Glulam | 30 | 1 | 30 | 54.34 | 1630.2
B10 | 6.75"x24" 24F-V4 DF Glulam | 13 | 1 | 13 | 54.34 | 706.42
B11 | 5.5"x24" 24F-V4 DF Glulam | 30 | 1 | 30 | 32.604 | 978.12
B12a,b | 6x6 rough sawn df | 7 | 2 | 14 | 3.6408 | 50.9709
B13 | 6x6 rough sawn df | 28 | 1 | 28 | 3.6408 | 101.9418
Total | [5 empty] | 9508.1089
Hardware
Item | Product |  |  | # | Price/unit | Total
Joist Brackets | [5 empty] | 750
Glulam Brackets | [5 empty] | 1000
Post Brackets | [5 empty] | 100
Fasteners | [5 empty] | 150
Misc | [5 empty] | 250
Total | [5 empty] | 2250
0.16667
Total | [5 empty] | 50577.122
Roof Calcs | [7 empty] | Loading |  | Roof Weight
Rafter Framing | [7 empty] | 1760 |  | Material | Weight psf
Material | Span (ft) | Board L. (ft) | # |  | Price/each | Total |  | 79200 |  | T&G Cedar
AJS 150 11-7/8 | 36 | 22 | 50 |  | 53.9 | 2695 |  |  |  | 5/8” Drywall | 2.75
AJS 150 11-7/8 | 36 | 22 | 22 |  | 53.9 | 1185.8 |  |  |  | 14” Fiberglass Batt | 0.56
Bevel Plate Sill |  | 192 | [7 empty] | 360 Series 14” TJI 2' o.c. | 3.3
Dbl-Bvl Plate Beam |  | 140 | [5 empty] | 8800 |  | 5/8” Plywood Sheathing | 2.1
Blocking |  | 208
Ridge Board |  | 140 | [7 empty] | 18ga Metal Roof
Overhang
USP LSTA24 Strap |  |  | 70 |  | 1.815
UPS TMU Hanger |  |  | 140 | [7 empty] | 8.71
Ridge Beams
Material | Wall L. (ft) | Board L. (ft) | # |  | Price/each | Total |  |  |  | Roof Design Load
[10 empty] | Dead | 15
[10 empty] | Live | 16
[10 empty] | Snow | 30
Columns
Trib Area Weights
[10 empty] | Partition | Width | Cor Factor | Corrected Width
[10 empty] | A | 18 | 1.2019 | 21.6333
[10 empty] | A' | 15.36 | 1.2019 | 18.4604
B
C
[10 empty] | D | 20 | 1.2019 | 24.037
[10 empty] | D Cos45 | 10.5064 | 0.63136 | 12.6272
[10 empty] | E | 17.99 | 1.2019 | 21.6213
[10 empty] | F | 18.27 | 1.2019 | 21.9578
G
Trib Loads plf
[10 empty] | Partition | Dead | Live | Snow
[10 empty] | A | 324.4996 | 288 | 540
[10 empty] | A' | 276.9063 | 245.76 | 460.8
B
C
[10 empty] | D | 360.5551 | 320 | 600
[10 empty] | D Cos45 | 189.4075 | 168.103 | 315.1932
[10 empty] | E | 324.3193 | 287.84 | 539.7
[10 empty] | F | 329.3671 | 292.32 | 548.1
G

## Insulation_Calcs
[6 empty] | Category | Cost
Crawlspace Insulation | [5 empty] | Crawlspace Insulation | 1780.1241
Item | Material | Length | Area (ft^2) | Price/unit | Total | Exterior Wall Insulation | 2557.5426
Crawlspace | 2” Rigid Insulation | 328 | 1312 | 1.3568 | 1780.1241 | Roof Insulation | 7597.9456
Total |  |  |  |  | 1780.1241
Exterior Wall Insulation | [5 empty] | Total | 11935.6123
Material | Wall L. (ft) | Wall H. (ft) | ft^2 | Price/ft^2 | Total
Cell. Blwn @ R-40 | 341 | 8 | 3137.2 | 0.47432 | 1488.0214
Netting | 341 | 8 |  |  | 525.0657
Garage Fib Batt | 60 | 9 | 540 | 1.0083 | 544.4555
Total |  |  |  |  | 2557.5426
Roof Insulation
Item | Material | Floor Area | ft^2 | Price/ft^2 | Total
Main Roof | R-49 Fiberglass Batt | 3456 | 4569.4 | 1.1547 | 5276.4004
Main Roof | R-3.2 Foam Board | 3456 | 4569.4 | 0.70472 | 3220.1561
Master Bed #1 | R-49 Fiberglass Batt | 512 | 593.67 | 1.1547 | 685.5256
Master Bed #2 | R-49 Fiberglass Batt | 512 | 593.67 | 1.1547 | 685.5256
Garage Ceiling | R-30 Fiberglass Batt | 864 | 950.4 | 1.0001 | 950.4979
Take Out R-3.2 Foam Board Insulation |  |  |  |  | -3220.16
Total |  |  |  |  | 7597.9456
Total |  |  |  |  | 11935.6123

## Finishing_Calcs
Drywall | [5 empty] | Category | Cost | [7 empty] | WINDOW SCHEDULE | [7 empty] | DOOR SCHEDULE
Walls | Wall L. (ft) | Height (ft) | ft^2 | Price/ft^2 | Total | Drywall | 8824.4099 |  | Gross Floor Areas |  |  | Wood | Tile | Carpet | # | WIDTH | HEIGHT | FRAME | HEAD HEIGHT | U-VALUE | TEMPERED | NOTES | # | WIDTH | HEIGHT | TRANS | HDWR SET | U.L LABLE | CONSTRUCTION | NOTES
Ext Inside Face | 410 | 8 | 3772 | 0.36272 | 1368.178 | Flooring | 14296.5215 |  | Room | Area |  |  |  |  | A | 72 | 48 | vinyl | 6'-8” | - | n | glider | 1 | 3'-0” | 6'-8” | ? | entry | n/a | - | exterior conventional hinged door
Int Both Sides | 1100 | 8 | 10120 | 0.36272 | 3670.7213 | Windows | 6399.437 |  | Master Bed E | 324.3 |  |  |  | 324.3 | B | 120 | 48 | vinyl | 6'-8” | - | n | glider | 2 | 5'-10” | 6'-8” | ? | entry | n/a | vinyl/glass | exterior french door
Ceilings Top |  |  | 4480 | 0.36272 | 1624.9834 | Doors | 14610.6568 |  | Master Bed E Bath | 128.9 |  |  | 128.9 |  | C | 42 | 60 | vinyl | 6'-8” | - | y | fixed | 3 | 3'-0” | 6'-8” | 0'-0” | passage | n/a | - | bathroom pocket door
Ceilings 1st Fl's |  |  | 2052 | 0.36272 | 744.3004 | Molding | 918.4635 |  | Master Bed E Closet | 63.1 | 516.3 |  |  | 63.1 | D | 42 | 60 | vinyl | 6'-8” | - | y | fixed | 4 | 3'-0” | 6'-8” | ? | entry | ? | - | garage conventional hinged door
Drywall Screws |  |  | 13211.775 | 0.019432 | 256.731 | Cabinetry / Counter-tops | 18800 |  | Master Bed W | 401.8 |  |  |  | 401.8 | E | 18 | 48 | vinyl | 6'-8” | - | y | glider | 5 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bathroom conventional hinged door
Drywall Tape |  |  | 5871.9 | 0.0086075 | 50.5421 | Sinks Toilets Showers Vanities | 8455 |  | Master Bed W Bath | 114.6 | 516.4 |  | 114.6 |  | F | 48 | 48 | vinyl | 6'-8” | - | y | glider | 6 | 3'-0” | 6'-8” | ? | entry | ? | - | garage conventional hinged door
Drywall Mud |  |  | 60.3651 | 8.0967 | 488.756 |  |  |  | Bedroom 1 | 200.8 |  |  |  | 200.8 | G | 48 | 48 | vinyl | 6'-8” | - | y | glider | 7 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bedroom conventional hinged door
Drywall Texture Mud |  |  | 76.5992 | 8.0967 | 620.1977 | Paint | 2360.9535 |  | Bedroom 2 | 269.7 |  |  |  | 269.7 | H | 48 | 48 | vinyl | 6'-8” | - | n | glider | 8 | 12'-0” | 6'-8” | ? | entry | n/a | vinyl/glass | patio bi-parting sliding door
Total |  |  |  |  | 8824.4099 | Misc | 250 |  | Bedroom 3 | 216 |  |  |  | 216 | I | 48 | 48 | vinyl | 6'-8” | - | n | glider | 9 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bedroom conventional hinged door
[9 empty] | Study | 289.3 |  | 289.3 |  |  | J | 48 | 48 | vinyl | 6'-8” | - | n | glider | 10 | 10'-0” | 8'-0” | ? | garage | n/a | panel | garage w/ remote opener
Flooring | [8 empty] | Bathroom | 137 |  |  | 137 |  | K | 48 | 48 | vinyl | 6'-8” | - | n | glider | 11 | 18”-0” | 8'-0” | ? | garage | n/a | panel | garage w/ remote opener
Flooring |  |  | ft^2 | Price/ft^2 | Total | Total | 74915.4422 |  | Hallway 1 | 95.2 |  | 95.2 |  |  | L | 96 | 48 | vinyl | 6'-8” | - | n | fixed | 12 | 6'-0” | 6'-8” | 0'-0” | passage | n/a | - | study french door
Hardwood |  |  | 2411 | 3.5756 | 8620.7041 |  |  |  | Hallway 2 | 81.8 |  | 81.8 |  |  | M | 18 | 48 | vinyl | 6'-8” | - | y | fixed | 13 | 4'-0” | 6'-8” | 0'-0” | passage | n/a | - | hallway french door
Tile |  |  | 511.9 | 3.2604 | 1668.9988 | [9 empty] | N | 18 | 48 | vinyl | 6'-8” | - | y | fixed | 14 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bedroom conventional hinged door
Cement Board |  |  | 511.9 | 0.74616 | 381.9573 | [9 empty] | O | 36 | 36 | vinyl | 6'-8” | - | n | glider | 15 | 2'8” | 6'-8” | 0'-0” | privacy | n/a | - | shower pocket door
Thinset |  |  | 511.9 | 0.15726 | 80.5014 |  |  |  | Living Room | 513.7 |  | 513.7 |  |  | P | 48 | 48 | vinyl | 6'-8” | - | n | glider | 16 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bathroom conventional hinged door
Grout |  |  | 511.9 | 0.072236 | 36.9776 |  |  |  | Kitchen | 273.2 |  | 273.2 |  |  | Q | 48 | 48 | vinyl | 6'-8” | - | n | glider | 17 | 4'-8” | 6'-8” | 0'-0” | passage | n/a | - | closet bi-fold door
Carpet |  |  | 1475.7 | 1.3911 | 2052.8522 |  |  |  | Dining Room | 249.5 |  | 249.5 |  |  | 2A | 48 | 48 | vinyl | 12'-2” | - | y | glider | 18 | 2'8” | 6'-8” | 0'-0” | privacy | n/a | - | water closet conventional hinged door
Carpet Padding |  |  | 1475.7 | 0.96725 | 1427.3738 |  |  |  | Foyer | 129.7 |  | 129.7 |  |  | 2B | 48 | 48 | vinyl | 12'-2” | - | y | glider | 19 | 4'-8” | 6'-8” | 0'-0” | passage | n/a | - | closet bi-fold door
Carpet Tack Strip |  |  | 500 | 0.054313 | 27.1564 |  |  |  | Utility | 69.7 |  |  | 69.7 |  | 2C | 48 | 48 | vinyl | 16'-2” | - | y | glider | 20 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bedroom conventional hinged door
[9 empty] | Spare Bath | 61.7 |  |  | 61.7 |  | 2D | 48 | 48 | vinyl | 12'-2” | - | y | glider | 21 | 3'-0” | 6'-8” | 0'-0” | privacy | n/a | - | bedroom conventional hinged door
Total |  |  |  |  | 14296.5215 |  |  |  | Total 1st floor | 3620 |  |  |  |  | 2E | 48 | 48 | vinyl | 12'-2” | - | y | glider | 22 | 4'-8” | 6'-8” | 0'-0” | passage | n/a | - | closet bi-fold door
[15 empty] | 2F | 48 | 48 | vinyl | 16'-2” | - | y | glider | 23 | 3'-0” | 6'-8” | 0'-0” | entry | ? | - | garage conventional hinged door
Windows | [8 empty] | Loft (finished) | 459 |  | 778.6 |  |  | 2G | 48 | 48 | vinyl | 16'-2” | - | y | glider | 24 | 2'-4” | 6'-8” | 0'-0” | passage | n/a | - | pantry conventional hinge door
Window | Size | Window Type | # | Price/Each | Total |  |  |  | Bonus Room East (unfinished) | 501.2 |  |  |  |  | 2H | 48 | 48 | vinyl | 16'-2” | - | y | glider | 25 | 3'-0” | 6'-8” | 0'-0” | passage | n/a | - | utility rm pocket door
Study and Masterbedrooms | 96x48" | end vent (?) sliding | 3 | 499.9823 | 1499.947 |  |  |  | Bonus Room West (unfinished) | 646.3 |  |  |  |  | 2I | 48 | 48 | vinyl | 16'-2” | - | y | glider | 26 | 2'-6” | 6'-8” | 0'-0” | passage | n/a | - | bathroom conventional hinge door
Bedrooms | 48x48" | left hand sliding | 3 | 321.3776 | 964.1329 |  |  | 1147.5 | Total 2nd floor | 1606.5 |  |  |  |  | 2J | 48 | 48 | vinyl | 16'-2” | - | y | glider | 27 | 2'-6” | 6'-8” | 0'-0” | passage | n/a | - | bathroom conventional hinge door
Master bedroom bathtub, laundry room | 48x48" | left hand sliding | 3 | 321.3776 | 964.1329 | [9 empty] | 2K | 48 | 48 | vinyl | 16'-2” | - | y | glider | 28 | 3'-0” | 6'-8” | ? | entry | n/a | - | front conventional hinge door
Master bedroom shower | 48x24" | awning | 1 | 286.274 | 286.274 |  |  |  | Total Finished Floor Area | 4079 |  | 2411 | 511.9 | 1475.7 | 2L | 48 | 48 | vinyl | 16'-2” | - | y | glider | A1 | 4'-8” | 6'-8” | 0'-0” | passage | n/a | - | attic room french
Great room wall- picture windows | 36x36" | picture | 6 | 216.534 | 1299.2042 | [17 empty] | A2 | 4'-8” | 6'-8” | 0'-0” | passage | n/a | - | attic room french
Guest bathroom (single hung) | 24x36" | single hung | 1 | 272.602 | 272.602 |  |  |  | Garage | 860.1
Front door side lights | 12x60" | picture? | 2 | 0 | 0
Great room large windows (or door panels)? | ? | ? | 4 | 0 | 0 |  |  |  | Gross Floor Area w/o Garage | 4079
Attic | 36x48" | single hung | 4 | 278.286 | 1113.144 |  |  |  | Gross Floor Area w/ Garage | 4939.1
Total |  |  |  |  | 6399.437 |  |  |  | Gross Floor Area w/ Garage + Attic | 6086.6
[12 empty] | 4822 | 1023.8 | 2951.4
Doors
Doors | Size | Door Type | # | Price/Each | Total
Front Door | 36x80” | Conventional | 1 | 1250.1569 | 1250.1569 | [6 empty] | 8797.2
Sliding Glass Grt Rm | 144x80" | 4 panel sliding glass | 1 | 3260.4 | 3260.4
French Door Mstr Bd | 76x80" | Conventional | 1 | 1682.4207 | 1682.4207 |  |  |  | Roof Area w/o Porches | 4640
Interior Door Pre-Hung | 36x80” | Conventional | 6 | 82.5425 | 495.2548 |  |  |  | Front Patio Porch | 240
Interior Door Pre-Hung | 32x80” | Conventional | 1 | 82.5425 | 82.5425 |  |  |  | Back Master Bed Porches | 480
Interior Door Pre-Hung | 30x80” | Conventional | 1 | 82.5425 | 82.5425 |  |  |  | Back Patio Porch | 250
Fire Door | 30x80” | Conventional | 3 | 216.2732 | 648.8196
Pocket Doors | 36x80” | Pocket | 1 | 128.2424 | 128.2424 |  |  |  | Total Roof Area w/ Porches | 5610
Pocket Doors | 32x80” | Pocket | 1 | 139.1104 | 139.1104
Pocket Door Frame | 36” | Pocket | 2 | 90.2044 | 180.4088
Closet Doors | 24x80” (2) | French | 6 | 82.5425 | 495.2548 |  |  |  | Garage Slab | 782
Hallway Door | 24x80” (2) | French | 2 | 82.5425 | 165.0849 |  |  |  | Front Porch Slab | 196
Study Doors | 36x80 (2) | French | 4 | 82.5425 | 330.1698 |  |  |  | Rear Porch Slab | 1184
Attic Doors | 36x80 (2) | French | 4 | 82.5425 | 330.1698 |  |  |  | Total Outside Concrete Pad Area | 2162
Garage Door | 10x8' | Garage Door | 1 | 1195.48 | 1195.48
Garage Door | 18x8' | Garage Door | 1 | 1096.5812 | 1096.5812
Garage Door Opener |  | Opener | 2 | 265.1792 | 530.3584
Door Hardware |  | Passage | 17 | 34.0566 | 578.9618 |  |  |  | Font Porch Roof | 240
Door Hardware |  | Privacy | 9 | 45.6229 | 410.6061 |  |  |  | Back Porch Roof | 682
Door Hardware |  | Entry | 7 | 204.0131 | 1428.0914 |  |  |  | Total Porch Roof Area | 922
Misc Hardware |  |  | 1 | 100 | 100
5621.1
5109.1
Total |  |  |  |  | 14610.6568
Molding
Item |  |  | ft | Price/unit | Total
Baseboards |  |  | 812 | 0.48091 | 390.4981
Window Sills |  |  |  |  | 250
Door Frames |  |  | 578 | 0.48091 | 277.9654
Total |  |  |  |  | 918.4635
Cabinetry / Counter-tops
Item |  |  | ft^2 | Price/ft^2 | Total
Kitchen Cabinets |  |  |  |  | 15000
Hallway Cabinets |  |  |  |  | 600
Bathroom Cabinets |  |  |  |  | 1200
Kitchen Concrete Countertops |  |  |  |  | 2000
Total |  |  |  |  | 18800
Sinks Toilets Showers Vanities
|  |  | # | Price/each | Total
Kitchen Sink |  |  | 1 | 250 | 250
Kitchen Faucet |  |  | 1 | 150 | 175
Mstr Bd Vanity + Sink |  |  | 1 | 1000 | 1000
Mstr Bd Vanity + Sink |  |  | 1 | 1000 | 1000
Bathroom Vanity+Sink |  |  | 1 | 1000 | 1000
Spare Bathroom Vanity+Sink |  |  | 1 | 500 | 500
Bathroom Faucets |  |  | 6 | 75 | 500
Shower 1 |  |  | 1 | 750 | 501
Shower 2 |  |  | 2 | 750 | 502
Shower 3 |  |  | 3 | 500 | 503
Bathtub Whirlpool |  |  | 1 | 1000 | 504
Bathtub |  |  | 1 | 500 | 505
Shower Faucet |  |  | 4 | 150 | 505
Bathtub Faucet |  |  | 2 | 100 | 505
Toilet |  |  | 4 | 182.5824 | 505
Total |  |  |  |  | 8455
Paint
Item | Length of Walls (ft) | Wall Height (ft) | Area ft^2 | Price/ft^2 | Total
Exterior Wall Paint | 400 | 9 | 3600 | 0.24986 | 899.4792
Exterior Trim Paint |  |  | 1000 | 0.24986 | 249.8553
Interior Wall Primer | 550 | 8 | 4400 | 0.050645 | 222.8375
Interior Paint | 550 | 8 | 4400 | 0.089607 | 394.2693
Interior Ceiling Primer |  |  | 3600 | 0.050645 | 182.3216
Interior Ceiling Paint |  |  | 3600 | 0.089607 | 322.584
Interior Trim |  |  | 1000 | 0.089607 | 89.6067
Total |  |  |  |  | 2360.9535
Misc
Item |  |  |  |  | Total
Smoke Alarms |  |  |  |  | 250
Fireplace → See Appliances
Wood Stove → See Appliances
Stairs → See Flatwork
Total |  |  |  |  | 250
Total |  |  |  |  | 74915.4422

## Appliances
Appliances Built-Ins |  |  |  | Category | Cost
Item | # | Price/Each | Total | Appliances Built-Ins | 12240.1374
Clothes Washer (Stackable) | 1 | 790.321 | 790.321
Clothes Dryer (Stackable) | 1 | 899.8704 | 899.8704
Dishwasher | 1 | 976.1638 | 976.1638 | Total | 12240.1374
Refrigerator | 1 | 1520.4332 | 1520.4332
Tankless Propane Water Heater | 1 | 1305.6054 | 1305.6054
Water Heater Pump & Control | 1 | 420.5916 | 420.5916
Gas Range Top | 1 | 977.0332 | 977.0332
Electric Double Oven | 1 | 1845.3864 | 1845.3864
Wood Stove | 1 | 1900.8132 | 1900.8132
Fireplace | 1 | 976.1638 | 976.1638
Range Hood | 1 | 281.4812 | 281.4812
Water Softener | 1 | 1497.0561 | 1497.0561
Water RO System | 1 | 556.3981 | 556.3981
Propane Tank | 1 | 3000 | 3000
Remove Washer& Dryer |  |  | -1689.69
Remove Refrigerator |  |  | -1520.43
Remove Water Softener |  |  | -1497.06
Total |  |  | 12240.1374

## HVAC
HVAC Units |  |  |  | Category | Cost
Item | # | Price/each | Total | HVAC Units | 13230
CX34 Chiller 2 Ton | 2 | 3795 | 7590 | Hydronic Plumbing | 500
Psychrologix™ DHC Controller | 2 | 395 | 790 | HRV System | 5000
CXI34 Air Handler | 5 | 539 | 2695
CXI65 Air Handler | 2 | 569 | 1138
Booster Pump | 1 | 289 | 289 | Total | 18730
HSE Corn Glycol (5 gal) | 2 | 114 | 228
Shipping |  |  | 500
Total |  |  | 13230
Hydronic Plumbing
Item | # | Price/ft | Total
PEX Pipe |  |  | 100
Fittings |  |  | 250
Expansion Tank |  |  | 50
Misc Hardware |  |  | 100
Total |  |  | 500
HRV System
Item | # |  | Total
5000
Total |  |  | 5000
18730

## Plumbing
Sewer Plumbing Rough In |  |  |  | Category | Cost | drainage fixture unit (d.f.u.) values for various plumbing fixtures from irc 2012 table p3004.1 |  | WATER SUPPLY FIXTURE UNIT TABLE PER IRC2012 TABLE 2903.6
Item | ft | Price/ft | Total | Sewer Plumbing Rough In | 2471 | TYPE OF FIXTURE OR GROUBP OF FIXTURES | (D.F.U) | type of fixture | water supply fixture unit value (w.s.f.u)
|  |  | 2471 | Water Pipe Rough In | 2471 | Bar sink | 1 |  | hot | cold | combined | # | total
|  |  |  | Gas Pipe Rough In | 250 | Bathtub (with or without shower head and/or whirlpool attachments) | 2 | bathtub | 1 | 1 | 1.4 | 0 | 0
[6 empty] | Bidet | 1 | clothes washer | 1 | 1 | 1.4 | 1 | 1.4
[6 empty] | Clothes washer standpipe | 2 | dishwasher | 1.4 | - | 1.4 | 0 | 0
|  |  |  | Total | 5192 | Dishwasher | 2 | full-bath group | 1.5 | 2.7 | 3.6 | 4 | 14.4
Total |  |  | 2471 |  |  | Floor drain | 0 | half-bath group | 0.5 | 2.5 | 2.6 | 0 | 0
[6 empty] | Kitchen sink | 2 | hose bibb | - | 2.5 | 2.5 | 5 | 12.5
Water Pipe Rough In | [5 empty] | Lavatory | 1 | kitchen group | 1.9 | 1 | 2.5 | 1 | 2.5
Item | ft | Price/ft | Total |  |  | Laundry tub | 2 | kitchen sink | 1 | 1 | 1.4 | 1 | 1.4
|  |  | 2471 |  |  | Shower stall | 2 | laundry group | 1.8 | 1.8 | 2.5 | 1 | 2.5
[6 empty] | Water closet (1.6 gpf) | 3 | laundry tub | 1 | 1 | 1.4 | 0 | 0
[6 empty] | Water closet (> 1.6 gpf) | 4 | lavatory | 0.5 | 0.5 | 0.7 | 0 | 0
[6 empty] | Full-bath group with bathtub (1.6 gpf, and with or without shower head and/or whirlpool attachment on the bathtub or shower stall) | 5 | shower stall | 1 | 1 | 1.4 | 0 | 0
[6 empty] | Full-bath group with bathtub (> 1.6 gpf, and with or without shower head and/or whirlpool attachment on the bathtub or shower stall) | 6 | water closet | - | 2.2 | 2.2 | 0 | 0
Total |  |  | 2471 |  |  | Half-bath group (1.6 gpf) plus lavatory) | 4
[6 empty] | Half-bath group (> 1.6 gpf) plus lavatory) | 5 | total (w.s.f.u) |  |  |  |  | 34.7
Gas Pipe Rough In | [5 empty] | Kitchen group (dishwasher and sink with or without garbage grinder) | 2 | pressure (psi) |  |  |  |  | 0
Item | ft | Price/ft | Total |  |  | Laundry group (clothes washer standpipe and laundry tub) | 3 | max dev. length |  |  |  |  | 0
|  |  | 250 |  |  | Multiple-bath groups
[6 empty] | 1.5 baths | 7
[6 empty] | 2 baths | 8
[6 empty] | 2.5 baths | 9
[6 empty] | 3 baths | 10
Total |  |  | 250 |  |  | 3.5 baths | 11
5192

## Septic
Eljin SDF Septic |  |  |  | Determining Fixture Count
Item |  |  | Total | Residential Fixture Type | Fixture Units | X | Qty | =
Septic Tank | 1 | 3000 | 3000 | Utility Tub or Sink | 2 | X | 1 | = | 2
Gravel for Septic Tank |  |  | 100 | Sink (bar) | 1 | X | 1 | = | 1
4” SDR-35 Perforated Pipe | 240 | 1.2486 | 299.6568 | Kitchen Sink w/ Dishwasher | 2 | X | 2 | = | 4
Filter | 1 | 75 | 75 | Dishwasher-additional | 2 | X | 0 | = | 0
Distribution Box | 1 | 60 | 60 | Sink (Double-as in Master Bath Room | 1 | X | 1 | = | 1
Riser | 1 | 60 | 60 | Sink | 1 | X | 5 | = | 5
4” Sewer Line to Tank | 80 | 1.628 | 130.2421 | Clothes Washer | 2 | X | 2 | = | 4
Sand ASTM C33 | 85.1 | 22.8228 | 1942.2203 | Shower (single stall) | 2 | X | 4 | = | 8
B43 Pad with fabric and hoops | 60 | 117.3744 | 7042.464 | Bathtub | 2 | X | 3 | = | 6
Misc | 1 | 150 | 150 | Toilet 1.6 gal per Flush (gpf) | 3 | X | 6 | = | 18
[5 empty] | TOTAL |  |  |  | 49
Total |  |  | 12859.5832 | R18-9-A314. Septic Tank Design, Manufacturing, and Installation for Onsite Wastewater Treatment Facilities
Criteria for Septic Tank Size and Design Flow : 7 Bed 49 Fixture Count → 2,500 Min Design Liquid Cap (gal), 1050 Design Flow (Gal/Day)
Quick 4+ HC Chambers Septic |  |  |  |  | SAR | = | 0.4
Item |  |  | Total |  | SARa | = | 0.88529
Septic Tank | 1 | 3500 | 3500 |  | Daily Design Flow | = | 1050
Gravel for Septic Tank |  |  | 100 |  | Absorption Area | = | 1186.0488
Filter | 1 | 75 | 75 |  | B43 Area (ft^2) | = | 20
Distribution Box | 1 | 60 | 60 |  | B43 Units Needed | = | 59.3024
Riser | 1 | 60 | 60 |  | B43 Units Used | = | 60
4” Sewer Line to Tank | 80 | 1.628 | 130.2421 |  | Trench Length Calc | = | 237.2098
Quick 4 Plus HC Chamber | 93 | 35.8535 | 3334.3785 |  | Trench Length Used | = | 240
Quick 4 Plus Endcap | 8 | 18.4756 | 147.8048 |  | Sand CS Area (ft^2) | = | 6.1667
Misc | 1 | 150 | 150 |  | Sand Volume (ft^3) | = | 1480
[5 empty] | Sand Density (lb/ft^2) | = | 100
[5 empty] | Sand Tons | = | 74
Total |  |  | 7557.4254 | Primary Black + Gray Water
|  |  |  | Residential Fixture Type | Fixture Units | X | Qty | =
|  |  |  | Utility Tub or Sink | 2 | X | 1 | = | 2
Aerobic System + Chambers |  |  |  | Sink (bar) | 1 | X | 1 | = | 1
Item |  |  | Total | Kitchen Sink w/ Dishwasher | 2 | X | 2 | = | 4
Septic Tank 1050 gal | 1 | 972 | 972 | Dishwasher-additional | 2 | X | 0 | = | 0
Gravel for Septic Tank |  |  | 100 | Sink (Double-as in Master Bath Room | 1 | X | 0 | = | 0
Filter | 1 | 75 | 75 | Sink | 1 | X | 1 | = | 1
Distribution Box | 1 | 60 | 60 | Clothes Washer | 2 | X | 0 | = | 0
Riser | 1 | 60 | 60 | Shower (single stall) | 2 | X | 0 | = | 0
4” Sewer Line to Tank | 80 | 1.628 | 130.2421 | Bathtub | 2 | X | 0 | = | 0
Quick 4 Plus HC Chamber | 46.5 | 35.8535 | 1667.1892 | Toilet 1.6 gal per Flush (gpf) | 3 | X | 6 | = | 18
Quick 4 Plus Endcap | 8 | 18.4756 | 147.8048 |  | TOTAL |  |  |  | 26
Aerobic Tank Setup |  |  | 7000
Control Panel |  |  | 300
Misc | 1 | 150 | 150 | Gray Water Only
|  |  |  | Residential Fixture Type | Fixture Units | X | Qty | =
|  |  |  | Utility Tub or Sink | 2 | X | 0 | = | 0
Total |  |  | 10662.2362 | Sink (bar) | 1 | X | 0 | = | 0
|  |  |  | Kitchen Sink w/ Dishwasher | 2 | X | 0 | = | 0
|  |  |  | Dishwasher-additional | 2 | X | 0 | = | 0
Aerobic System + Subsurface Pressure Drip Line |  |  |  | Sink (Double-as in Master Bath Room | 1 | X | 0 | = | 0
Item |  |  | Total | Sink | 1 | X | 5 | = | 5
Septic Tank 1050 gal | 1 | 972 | 972 | Clothes Washer | 2 | X | 2 | = | 4
Gravel for Septic Tank |  |  | 100 | Shower (single stall) | 2 | X | 4 | = | 8
Filter | 1 | 75 | 75 | Bathtub | 2 | X | 3 | = | 6
Distribution Box | 1 | 60 | 60 | Toilet 1.6 gal per Flush (gpf) | 3 | X | 0 | = | 0
Riser | 1 | 60 | 60 |  | TOTAL |  |  |  | 23
4” Sewer Line to Tank | 80 | 1.628 | 130.2421
Drip Tubing | 46.5 | 35.8535 | 1000
Distribution tubing and fittings | 8 | 18.4756 | 250 | [5 empty] | 49
Aerobic Tank Setup |  |  | 7000
Effluent Pump | 1 | 500 | 250
Control Panel |  |  | 300
Misc | 1 | 150 | 250
Total |  |  | 10447.2421

## Elec_Calcs
Electric |  |  |  | Category | Cost
Item | ft^2 | Price/ft^2 | Total | Electric | 9481
Lighting Fixtures |  |  | 4030
Wiring |  |  | 5451
Outlets |  |  |  | Total | 9481
Cat5
Total |  |  | 9481

## FireSprinkler
Fire Sprinklers |  | Category | Cost
Item | Total | Fire Sprinklers | 10330
10330
|  | Total | 10330
Total | 10330
https://www.darley.com/starterpaq
nfpa13d
https://www.generalairproducts.com/fire-protection-products/nfpa-13d-residential-pump-and-tank-packages.html
http://www.raimondofiresystems.com/

## Heat_Calcs
Wall Assembly R Calcs
[8 empty] | Framing | Cavity
Framing factor assumptions: No stud bridging, 1” for top plate and 1” for sub floor bridging, 1” x 10' bridging per bay for Window and door framing | [5 empty] | Wall-Outside Air Film(wntr) |  | 0.17 | 0.17
|  | Cavity dim | 22.5” x 96” | 2160 |  | Siding – Hardboard |  | 0.34 | 0.8
|  | Top/Bottom | 2” x 24” (2) | 96 |  | Plywood Sheathing - 1/2" |  | 0.63 | 0.63
|  | Wind/Door | 1” x 120” | 120 |  | 10" Cellulose |  |  | 38
|  | Calc FF |  | 10% |  | 10" Thick Wood Bridging |  | 12.5
[6 empty] | 1/2" Drywall |  | 0.45 | 0.45
[6 empty] | Inside Air Film |  | 0.68 | 0.68
[6 empty] | Framing Factor |  | 10% | 90%
[6 empty] | Total Wall Component R |  | 14.87 | 40.73
[6 empty] | Wall Component U |  | 0.067249 | 0.024552
[6 empty] | Total Wall Assembly R |  | 34.6961
[6 empty] | Total Wall Assembly U |  | 0.028822
Roof Assembly R Calcs
[8 empty] | Framing | Cavity
Framing factor assumptions: 24” oc spacing of 14” TJI, 2” ridge board and blocking | [5 empty] | Wall-Outside Air Film(wntr) |  | 0.17 | 0.17
|  | Cavity dim | 22.5” x 24' | 6480 |  | Siding –
|  | Top/Bottom | 2” x 24” (2) | 96 |  | Plywood Sheathing - 1/2" |  | 0.63 | 0.63
[6 empty] | 12" Fiberglass Batts |  |  | 38
|  | Calc FF |  | 1.481% |  | 14" Thick Wood Bridging |  | 17.5
[6 empty] | 1/2" Drywall |  | 0.45 | 0.45
[6 empty] | Inside Air Film |  | 0.68 | 0.68
[6 empty] | Framing Factor |  | 1.481% | 98.52%
[6 empty] | Total Wall Component R |  | 19.4448 | 39.93
[6 empty] | Wall Component U |  | 0.051428 | 0.025044
[6 empty] | Total Wall Assembly R |  | 39.3164
[6 empty] | Total Wall Assembly U |  | 0.025435
Floor Assembly R Calcs
[8 empty] | Framing | Cavity
Framing factor assumptions: 16” oc spacing of 9.5” TJI, 2” rim board and blocking. Assume crawlspace insulation value X1.5 due to airspace | [5 empty] | Wall-Outside Air Film(wntr) |  | 0.17 | 0.17
|  | Cavity dim | 14.5” x 18' | 3132 |  | Siding –
|  | Top/Bottom | 2” x 16” (2) | 64 |  | Plywood Sheathing – 7/8" |  | 1.0938 | 1.0938
|  | Wind/Door | 1” x 120” |  |  | 12" Fiberglass Batts |  | 45 | 45
|  | Calc FF |  | 2.043% |  | 10" Thick Wood Bridging |  | 12.5
[6 empty] | 1/2" Drywall |  | 0.45 | 0.45
[6 empty] | Inside Air Film |  | 0.68 | 0.68
[6 empty] | Framing Factor |  | 10% | 90%
[6 empty] | Total Wall Component R |  | 59.9937 | 47.3937
[6 empty] | Wall Component U |  | 0.016668 | 0.0211
[6 empty] | Total Wall Assembly R |  | 48.4105
[6 empty] | Total Wall Assembly U |  | 0.020657
North Wall
| Wall |  |  |  |  | Windows |  |  |  | Doors |  |  |  | Thermal Brake
| W | H | A | U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| 96 | 8 | 768 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34 | 3 | 6.6667 | 20 | 0.2 | 0 | 0 | 0 | 2
| 18 | 12 | 216 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 8 | 4 | 32 | 0.34
[6 empty] | 1.5 | 4 | 6 | 0.34
[6 empty] | 1.5 | 4 | 6 | 0.34
[6 empty] | 3.6667 | 2 | 7.3333 | 0.34
SUM | 114 | 20 | 984 | - |  | 33 | 32.3333 | 118.5556 | - | 3 | 6.6667 | 20 | - | 0 | 0 | 0 | -
North Wall Assembly | [5 empty] | Floor area to Glazing |  | 3.293%
Element | Area ft^2 | U-Factor | Area * U-Factor
Total Area | 984
Wall | 845.4444 | 0.028822 | 24.3671
Window | 118.5556 | 0.34 | 40.3089
Doors | 20 | 0.2 | 4
Thermal Brake | 0 | 2 | 0
Glazing % | 14.02%
SUM |  |  | 68.676
Average U-Factor | 0.069793 | Average R- | 14.3281
South Walls
| Wall |  |  |  |  | Windows |  |  |  | Doors |  |  |  | Thermal Brake
| W | H | A | U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| 96 | 8 | 768 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34 |  |  |  |  | 0 | 0 | 0 | 2
| 18 | 12 | 216 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
| 16 | 5 | 80 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
| 16 | 5 | 80 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 12 | 6.6667 | 80 | 0.34
[6 empty] | 12 | 6.6667 | 80 | 0.34
[6 empty] | 6 | 6.6667 | 40 | 0.34
[6 empty] | 6 | 6.6667 | 40 | 0.34
[6 empty] | 3.4167 | 5 | 17.0833 | 0.34
[6 empty] | 3.4167 | 5 | 17.0833 | 0.34
[6 empty] | 3.4167 | 5 | 17.0833 | 0.34
[6 empty] | 3.4167 | 5 | 17.0833 | 0.34
SUM | 146 | 30 | 1144 | - |  | 79 | 76 | 415.8889 | - | 0 | 0 | 0 | - | 0 | 0 | 0 | -
South Walls Assembly | [5 empty] | Floor area to Glazing |  | 11.55%
Element | Area ft^2 | U-Factor | Area * U-Factor
Total Area | 1144
Wall | 728.1111 | 0.028822 | 20.9854 | 24
Window | 415.8889 | 0.34 | 141.4022 | 141
Doors | 0 | 0 | 0
Thermal Brake | 0 | 2 | 0
Glazing % | 57.12%
SUM |  |  | 162.3876 | 165
Average U-Factor | 0.14195 | Average R- | 7.0449 | 6.9
East Wall
| Wall |  |  |  |  | Windows |  |  |  | Doors |  |  |  | Thermal Brake
| W | H | A | U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| 52 | 8 | 416 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34 |  |  |  |  | 0 | 0 | 0 | 2
| 18 | 12 | 216 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
[6 empty] | 3.6667 | 3.6667 | 13.4444 | 0.34
SUM | 70 | 20 | 632 | - |  | 18.3333 | 18.3333 | 67.2222 | - | 0 | 0 | 0 | - | 0 | 0 | 0 | -
East Wall Assembly | [5 empty] | Floor area to Glazing |  | 1.867%
Element | Area ft^2 | U-Factor | Area * U-Factor
Total Area | 632
Wall | 564.7778 | 0.028822 | 16.2778
Window | 67.2222 | 0.34 | 22.8556
Doors | 0 | 0 | 0
Thermal Brake | 0 | 2 | 0
Glazing % | 11.9%
SUM |  |  | 39.1334
Average U-Factor | 0.06192 | Average R- | 16.1499
West Walls
| Wall |  |  |  |  | Windows |  |  |  | Doors |  |  |  | Thermal Brake
| W | H | A | U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| 52 | 8 | 416 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34 |  |  |  |  | 0 | 0 | 0 | 2
| 18 | 12 | 216 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
| 16 | 8 | 128 | 0.028822 |  | 3.6667 | 3.6667 | 13.4444 | 0.34
SUM | 86 | 28 | 760 | - |  | 11 | 11 | 40.3333 | - | 0 | 0 | 0 | - | 0 | 0 | 0 | -
West Wall Assembly | [5 empty] | Floor area to Glazing |  | 1.12%
Element | Area ft^2 | U-Factor | Area * U-Factor
Total Area | 760
Wall | 719.6667 | 0.028822 | 20.742
Window | 40.3333 | 0.34 | 13.7133
Doors | 0 | 0 | 0
Thermal Brake | 0 | 2 | 0
Glazing % | 5.604%
SUM |  |  | 34.4553
Average U-Factor | 0.045336 | Average R- | 22.0575
Roof Assembly
| Roof | [12 empty] | Thermal Brake
| W | H | A | U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| 96 | 21.6 | 2073.6 | 0.033333 | [9 empty] | 0 | 0 | 0 | 2
| 96 | 21.6 | 2073.6 | 0.033333
| 16.75 | 16 | 268 | 0.033333
| 16.75 | 16 | 268 | 0.033333
SUM | 225.5 | 75.2 | 4683.2 | - |  | 0 | 0 | 0 | - | 0 | 0 | 0 | - | 0 | 0 | 0 | -
Roof Assembly | [5 empty] | Floor area to Glazing |  | 0%
Element | Area ft^2 | U-Factor | Area * U-Factor
Total Area | 4683.2
Wall | 4683.2 | 0.033333 | 156.1067
Window | 0 | 0 | 0
Doors | 0 | 0 | 0
Thermal Brake | 0 | 2 | 0
Glazing % | 0%
SUM |  |  | 156.1067
Average U-Factor | 0.033333 | Average R- | 30
Floor Assembly
| Roof | [12 empty] | Thermal Brake
| W | H | A | U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| 96 | 36 | 3456 | 0.033333 | [9 empty] | 0 | 0 | 0 | 2
| 32 | 16 | 512 | 0.033333
| 32 | 16 | 512 | 0.033333
SUM | 160 | 68 | 4480 | - |  | 0 | 0 | 0 | - | 0 | 0 | 0 | - | 0 | 0 | 0 | -
Floor Assembly | [5 empty] | Floor area to Glazing |  | 0%
Element | Area ft^2 | U-Factor | Area * U-Factor
Total Area | 4480
Wall | 4480 | 0.033333 | 149.3333
Window | 0 | 0 | 0
Doors | 0 | 0 | 0
Thermal Brake | 0 | 2 | 0
Glazing % | 0%
SUM |  |  | 149.3333
Average U-Factor | 0.033333 | Average R- | 30
House Complete Assembly
| Assembly | [12 empty] | Thermal Brake
| Element | Area ft^2 | U-Factor | Area * U-Factor |  | W | H | A | U-Factor | W | H | A | U-Factor | W | H | A | U-Factor
| N Wall | 984 | 0.069793 | 68.676 | [9 empty] | 0 | 0 | 0 | 2
| S Wall | 1144 | 0.14195 | 162.3876
| E Wall | 632 | 0.06192 | 39.1334
| W Wall | 760 | 0.045336 | 34.4553
| Roof | 4683.2 | 0.033333 | 156.1067
| Floor | 4480 | 0.033333 | 149.3333
| SUM | 12683.2 |  | 610.0924
| Heat Loss / Day / deg F |  |  | 14642.217 |  | 7321.1085
219633.2544
| Dewey HDD (65F) |  |  | 5400 |  | 26317.8822
|  |  |  | 4500 |  | 526.3576
| Yearly Heat |  |  | 79067971.5822
| Yearly Cool |  |  | 65889976.3185
-
Electric Rate Calcs | [5 empty] | Design Day Calcs |  |  |  | Water Storage Calcs
1 kwhr = | 3412.14 | btu |  |  |  | Design heat delta |  | 45 |  | Water lb to gal |  | 8.3454
On Peak $ / kwhr | 0.24477 |  |  |  |  | Design heat BTU / hr |  | 27454.1568 |  | Heat loss / 7 hours / deg F |  | 4270.6466
Off Peak $ / kwhr | 0.06118 |  |  |  |  | Design cold delta |  | 40 |  | Outside-Inside delta T |  | 30
Standard $ / kwhr | 0.13817 |  |  |  |  | Design cold BTU / hr |  | 24403.6949 |  | Total Heat loss / 7 hours |  | 128119.3984
[6 empty] | Design Cold Ton AC |  | 2.0336 |  | Heat storage delta T |  | 30
Winter COP | 2
Summer COP | 3.5 | [8 empty] | Gallons of water required |  | 511.7366
Winter Cost | 1600.8754
Summer Cost | 762.3216
Yearly Cost | 2363.1969
Average Cost / Month | 196.9331
Small spare bedroom | 11.83x16.9 | 199.927 | 0.66667
percent of house |  | 0.055535
heat btu |  | 1524.6742
cold btu |  | 1355.266
CX34 Chiller ODU up to 2 Tons Cooling, 3 Tons Heating DC Inverter Compressor, includes VSD Pump - See more at: http://www.chiltrix.com/documents/price-list.html#sthash.AR7G8kaA.dpuf |  |  |  | 3795 | 2 | 7590
Psychrologix™ DHC Controller |  |  |  | 395 | 2 | 790
CXI34 Indoor Unit up to 3,379 BTU Cooling/ 3,347 BTU Heating 120v DC Inverter 5.1" Thin - See more at: http://www.chiltrix.com/documents/price-list.html#sthash.AR7G8kaA.dpuf |  |  |  | 539 | 8 | 4312
12692

## Electric Calcs
ELECTRICAL LOAD CALCULATIONS |  |  | PANEL SCHEDULE
400 AMP MB PANEL 120/240 V 1PH. -3W
5230 S.F x 3 WATTS | 15690 | WATTS | CRKT | DESCRIPTION | WIRE | BRK | BRK | WIRE | DESCRIPTION | CRKT
RANGE OVEN | 8000 | WATTS | 1 | sub pnl, shop | #2 | 2P-200 | 1P-20 | #12 | bath gfci | 2
ELEC DRYER | 5000 | WATTS | 3 | sub pnl, shop | #2 | 2P-200 | 1P-20 | #12 | bath gfci | 4
JET TUB | 1500 | WATTS | 5 | 2 ton hp #1 | #12 | 2P-200 | 1P-20 | #12 | bath gfci | 6
BATH GFCI X2 | 3000 | WATTS | 7 | 2 ton hp #1 | #12 | 2P-200 | 1P-20 | #12 | bath gfci | 8
DOOR MOTOR | 1500 | WATTS | 9 | 2 ton hp #2 | #12 | 2P-200 | 1P-20 | #12 | garage gfci | 10
DUCTLESS FANS | 3000 | WATTS | 11 | 2 ton hp #2 | #12 | 2P-200 | 1P-20 | #12 | garage gfci | 12
CLOTHES WASHER | 1500 | WATTS | 13 | Oven | #6 | 2P-50 | 1P-20 | #12 | appliance | 14
LAUNDRY | 1500 | WATTS | 15 | Oven | #6 | 2P-50 | 1P-20 | #12 | appliance | 16
APPLIANCE X2 | 3000 | WATTS | 17 | Garage 220 | #6 | 2P-50 | 1P-20 | #12 | appliance | 18
REFRIGERATOR | 1500 | WATTS | 19 | Garage 220 | #6 | 2P-50 | 1P-20 | #12 | dw/disposal gfci | 20
DW/DISPOSAL | 2250 | WATTS | 21 | dryer | #10 | 2P-30 | 1P-20 | #12 | rec afci | 22
|  |  | 23 | dryer | #10 | 2P-30 | 1P-20 | #12 | rec afci | 24
TOTAL | 47440 | WATTS | 25 | fan coils | #12 | 1P-20 | 1P-20 | #12 | rec afci | 26
|  |  | 27 | fan coils | #12 | 1P-20 | 1P-20 | #12 | rec afci | 28
1ST 10KW AT 100% | 10000 | WATTS | 29 | whirlepool tub | #12 | 1P-20 | 1P-20 | #12 | rec afci | 30
47440W AT 40% | 14976 | WATTS | 31 | lights afci | #14 | 1P-15 | 1P-20 | #12 | rec afci | 32
TOTAL | 24976 | WATTS | 33 | lights afci | #14 | 1P-15 | 1P-20 | #12 | rec afci | 34
24976/240V | 104.0667 | AMPS | 35 | lights afci | #14 | 1P-15 | 1P-20 | #12 | rec afci | 36
HEAT PUMP #1 | 13 | AMPS | 37 | lights afci | #14 | 1P-15 | 1P-20 | #12 | ext gfci | 38
HEAT PUMP #2 | 13 | AMPS | 39 | lights afci | #14 | 1P-15 | 1P-20 | #12 | ext gfci | 40
|  |  | 41 | lights afci | #14 | 1P-15
TOTAL SERVICE LOAD | 130.0667 | AMPS

## Design_Criteria
TABLE R301.2(1)
CLIMATIC AND GEOGRAPHICAL DESIGN CRITERIA GORY
GROUND SNOW LOAD | WIND DESIGN |  | SEISMIC DESIGN CATEGORYf | Weatheringa | Frost line depthb | Termitec | WINTER DESIGN TEMPe | ICE BARRIER UNDERLAYMENT REQUIREDh | FLOOD HAZARDSh | AIR FREEXING INDEXi | MEAN ANNUAL TEMPj
| SPEED (mph) | Topographical Effectsk
30psf | 90 exp C |  | C | NEGLIGABLE | 18” |  |  | No
For SI: 1 pound per square foot - 0.0479 kPa, I mile per hour = 0.447 m/s. a. Weathering may require a higher strength concrete or grade of masonry than necessary to satisfy the structural requirements of this code. The weathering column shall be filled in with the weathering index (i.e., "negligible," "moderate" or "severe") for concrete as determined from the Weathering Probability Map [Figure R301.2(3)]. The grade of masonry units shall be determined from ASTM C 34, C 55, C 62, C 73, C 90, C 129, C 145,C 216 or C 652. b. The frost line depth may require deeper footings than indicated in Figure R403.1(1). The jurisdiction shall fill in the frost line depth column with the minimum depth of footing below finish grade. c. Thejurisdiction shall fill in this part of the table to indicate the need for protection depending on whether there has been a history of local subterranean termite damage. d. The jurisdiction shall fill in this part of the table with the wind speed from the basic wind speed map [Figure R301.2(4)A], Wind exposure category shall be determined on a site-specific basis in accordance with Section R301.2.1.4. e. The outdoor design dry-bulb temperature shall be selected from the columns of 9772-percent values for winter from Appendix Dof the InternationalPlumbing Code. Deviations from the Appendix D temperatures shall be permitted to reflect local climates or local weather experience as determined by the building official. f. The jurisdiction shall fill in this part of the table with the seismic design category determined from Section R301.2.2.1. g. The jurisdiction shall fill in this part of the table with (a) the date of the jurisdiction's entry into the National FloodInsurance Program (date of adoption of the first code or ordinance for management of flood hazard areas), (b) the date(s) of the Flood Insurance Study and (c) the panel numbers and dates of all currently effective FIRMs and FBFMs or other flood hazard map adopted by the authority having jurisdiction, as amended. h. Inaccordance with Sections R905.2.7.1,R905.4.3.1, R905.5.3.1,R905.6.3.1, R905.7.3.1 and R905.8.3.1, where there has been a history of local damage from the effects of ice damming, the jurisdiction shall fill in this part of the table with "YES." Otherwise, the jurisdiction shall fill in this part of the table with "NO." i. The jurisdiction shall fill in this part of the table with the 100-year return period air freezing index (BF-days) from Figure R403.3(2) or from the 100-year (99 percent) value on the National Climatic Data Center data table "Air Freezing Index-USA Method (Base 32°F)" at www.ncdc.noaa.gov/fpsf.html. j. The jurisdiction shall fill in this part of the table with the mean annual temperature from the National Climatic Data Center data table "Air Freezing Index- USA Method (Base 32°F)" at www.ncdc.noaa.gov/fpsf.html. k. In accordance with Section R301.2.1.5, where there is local historical data documenting structural damage to buildings due to topographic wind speed-up effects, the jurisdiction shall fill in this part of the table with "YES." Otherwise, the jurisdiction shall indicate "NO" in this part of the table.
Zoning/Density Regulations (in feet unless otherwise noted)
Dist. | Min Lot Size (in Sq. Ft. per Dwelling) | Min Lot Width and Depth | Min Yard Setbacks Min Building Spacing is 10 Feet All Classes |  |  |  | Max Building Height (Stories/Feet) |  | Max Lot Coverage (Percent)
|  |  | Front | Rear | Interior | Exterior
70 | 70000 | 200 | 50 | 50 | 25 | 30 | 2 | 30 | 15

## Retail_Prices
Item | Unit Size | Sale Unit Size | Unit (column H) | Retail Price | Tax Rate | Total Price /Each | Price /Single Unit | Supplier
Concrete Block | 8”x8”x16” | 1 | each | 1.2 | 0.0868 | 1.3042 | 1.3042 | http://www.homedepot.com/p/8-in-x-8-in-x-16-in-Concrete-Block-100825/202323962
Concrete MW Blocl (non-load bearing) | 6”x8”x16” | 1 | each | 1.65 | 0.0868 | 1.7932 | 1.7932 | http://www.homedepot.com/p/6-in-x-8-in-x-16-in-Concrete-MW-Block-6816/3017552301.238952
Red Medium Brick | 2 1/4”x3 5/8” 8” | 1 | each | 1.19 | 0.0868 | 1.2933 | 1.2933 | Yavapai Block 928-445-4340, would have to order from phx
Standard Brick | 2 1/4”x3 5/8” 7 5/8” | 1 | each | 0.65 | 0.0868 | 0.70642 | 0.70642 | http://phxbrickyard.com 602-258-7158 $0.60/ brick maybe a little less, add a dime for tumbling
22-Gauge Brick Tie | 100 | 100 | each | 15.77 | 0.0868 | 17.1388 | 0.17139 | http://www.homedepot.com/p/Simpson-Strong-Tie-22-Gauge-Brick-Tie-100-Pack-BT-R100/100375148
Flashing | 4'x4'x10' | 10 | ft | 12.57 | 0.0868 | 13.6611 | 1.3661 | http://www.homedepot.com/p/Construction-Metals-4-in-x-4-in-x-10-ft-Galvanized-Steel-L-Flashing-LF44G/202093207
Morter, Type S | 70 lb bag | 1 | each | 11.35 | 0.0868 | 12.3352 | 12.3352 | http://www.homedepot.com/p/Quikrete-70-lb-Type-S-Masonry-Cement-112571/100318458
Sand, Masonary | yd | 1 | yd^3 | 16 | 0.0868 | 17.3888 | 17.3888
Concrete Delivered | 1 yard | 1 | yd^3 | 100 | 0.0868 | 108.68 | 108.68 | Arrowhead Materials
ABC Fill Delivered | $17/Ton @ 140 lb/ft^3 | 1 | ft^3 | 1.19 | 0.0868 | 1.2933 | 1.2933 | http://www.prescottdirt.com/portfolio-item/abc/
¾ Ideal Mix | $29/Ton | 1 | ft^3 | 29 | 0.0868 | 31.5172 | 31.5172 | http://www.acmesand.com/semi-loads/
Rebar #4 (1/2”) | $7.25 / 1/2” x 20' | 20 | ft | 6.97 | 0.0868 | 7.575 | 0.37875 | http://www.homedepot.com/p/1-2-in-x-20-ft-Rebar-REB-4-615G4-20/202532809
Anchor Bolts | $79.98 / 50 (18”x1/2”) | 50 | each | 79.98 | 0.0868 | 86.9223 | 1.7384 | http://www.homedepot.com/p/Grip-Rite-18-in-x-0-5-in-Hot-Galvanized-Anchor-Bolt-50-Pieces-per-Box-1218GAB50/100190687
Lumber 2”x3”x8' #2 Doug Fir | 2x4x8 | 8 | ft | 2.1 | 0.0868 | 2.2823 | 0.28529 | https://www.lowes.com/pd/Common-2-in-x-3-in-x-8-Ft-Actual-1-5-in-x-2-5-in-x-7-9375-Feet-Stud/1000016683
Lumber 2”x4”x8' #2 Doug Fir | 2x4x8 | 8 | ft | 3.58 | 0.0868 | 3.8907 | 0.48634 | https://www.lowes.com/pd/Common-2-in-x-4-in-x-8-ft-Actual-1-5-in-x-3-5-in-x-8-ft-Stud/1000028847
Lumber 2x4x12 #2 Doug Fir | 2”4”12' | 12 | ft | 4.21 | 0.0868 | 4.5754 | 0.38129 | http://www.homedepot.com/p/2-in-x-4-in-x-10-ft-Standard-and-Better-Kiln-Dried-Heat-Treated-Spruce-Pine-Fir-Lumber-161659/100080482
Lumber 2”x4”x20' #2 Doug Fir | 2”x4”x20' | 20 | ft | 8.43 | 0.0868 | 9.1617 | 0.45809 | http://www.homedepot.com/p/2-in-x-4-in-x-20-ft-Premium-Standard-and-Better-Douglas-Fir-Lumber-150932/202094154
Lumber 2”x4”x20' Pressure Treated | 2”x4”x20' | 20 | ft | 14.37 | 0.0868 | 15.6173 | 0.78087 | http://www.homedepot.com/p/2-in-x-4-in-x-20-ft-Hem-Fir-Brown-Stain-Ground-Contact-Pressure-Treated-Lumber-Actual-1-5-in-x-3-5-in-x-240-in-17463-20/206949479
Lumber 2”x6”x8' #2 Doug Fir | 2”x6”x8' | 8 | ft | 4.86 | 0.0868 | 5.2818 | 0.66023 | http://www.homedepot.com/p/2-in-x-6-in-x-8-ft-2-and-Better-Kiln-Dried-Douglas-Fir-Board-HCF-KDDF-PRIME-2x6x8/206804068
Lumber 2”x6”x10' #2 Doug Fir | 2”x6”x10' | 10 | ft | 7.83 | 0.0868 | 8.5096 | 0.85096 | http://www.homedepot.com/p/2-in-x-6-in-x-10-ft-2-and-Better-Kiln-Dried-Douglas-Fir-Board-HCF-KDDF-PRIME-2x6x10/206804069
Lumber 2”6”x20' | 2”x6”x20' | 20 | ft | 12.13 | 0.0868 | 13.1829 | 0.65914 | http://www.homedepot.com/p/2-in-x-6-in-x-20-ft-Premium-2-and-Better-Douglas-Fir-Lumber-185469/202094171
Lumber 2”x6”x20' Pressure Treated | 2”x6”x20' | 20 | ft | 21.27 | 0.0868 | 23.1162 | 1.1558 | http://www.homedepot.com/p/2-in-x-6-in-x-20-ft-Hem-Fir-Brown-Stain-Ground-Contact-Pressure-Treated-Lumber-Actual-1-5-in-x-5-5-in-x-240-in-17464-20/206950057
Lumber 2”x8”x8' #2 Doug Fir | 2”x8”x12' | 8 | ft | 9.51 | 0.0868 | 10.3355 | 1.2919 | https://www.lowes.com/pd/Top-Choice-Common-2-in-x-8-in-x-8-ft-Actual-1-562-in-x-7-5-in-x-8-ft-Lumber/1000009802
Lumber 2”x8”x20' #2 Doug Fir | 2”x8”x20' | 20 | ft | 20.49 | 0.0868 | 22.2685 | 1.1134 | https://www.lowes.com/pd/Top-Choice-Common-2-in-x-8-in-x-20-ft-Actual-1-562-in-x-7-5-in-x-20-ft-Lumber/1000009760
Lumber 2”x10”x12' #2 Doug Fir
Lumber 2”x10”x12' #2 Doug Fir | 2”x10”x12' | 12 | ft | 13.97 | 0.0868 | 15.1826 | 1.2652 | http://www.homedepot.com/p/2-in-x-10-in-x-12-ft-2-and-Better-Prime-Douglas-Fir-Board-603708/206182035
Lumber 2”x10”x12' #2 Doug Fir | 2”x10”x14' | 14 | ft | 16.5 | 0.0868 | 17.9322 | 1.2809
Lumber 2”x10”x16' #2 Doug Fir | 2”x10”x16' | 16 | ft | 18.66 | 0.0868 | 20.2797 | 1.2675 | http://www.homedepot.com/b/Lumber-Composites-Framing-Lumber-Studs-Dimensional-Lumber/N-5yc1vZc55w/Ntk-Extended/Ntt-2x10x16?Ntx=mode+matchpartialmax&NCNI-5
Lumber 2”x10”x16' #2 Doug Fir | 2”x10”x16' | 16 | ft | 20.74 | 0.0868 | 22.5402 | 1.4088 | Foxworth Galbrath 928-445-2525 2/15/17
Lumber 2”x10”x20' #2 Doug Fir | 2”x10”x20' | 20 | ft | 23.34 | 0.0868 | 25.3659 | 1.2683 | http://www.homedepot.com/p/2-in-x-10-in-x-20-ft-Premium-2-and-Better-Douglas-Fir-Lumber-714755/202094203
Lumber 2”x12”x16' #2 Doug Fir | 2”x10”x16' | 16 | ft | 21.6 | 0.0868 | 23.4749 | 1.4672 | http://www.homedepot.com/p/2-in-x-12-in-x-16-ft-2-and-Better-Prime-Kiln-Dried-Heat-Treated-Doug-Fir-Lumber-2x12-16-2-btr-kd-prime-doug-fir/300187825
Lumber 2”x12”x20' #2 Doug Fir | 2”x10”x20' | 20 | ft | 21.6 | 0.0868 | 23.4749 | 1.1737 | Foxworth Galbrath 928-445-2525 2/15/17
Lumber Rough Sawn | 2”x12”x20' | 1 | ft | 3.23 | 0.0868 | 3.5104 | 3.5104 | http://www.hesterslogandlumber.com/rough-cut-lumber-pricesheet.html
Lumber Rough Sawn | 3”x12”x20' | 1 | ft | 4.84 | 0.0868 | 5.2601 | 5.2601 | http://www.hesterslogandlumber.com/rough-cut-lumber-pricesheet.html
Lumber Rough Sawn | 4”x4”x20' | 1 | ft | 1.4 | 0.0868 | 1.5215 | 1.5215 | http://www.hesterslogandlumber.com/rough-cut-lumber-pricesheet.html
Lumber Rough Sawn | 6”x6”x20' | 20 | ft | 67 | 0.0868 | 72.8156 | 3.6408 | https://northlandwood.com/roughlumber/
Lumber Rough Sawn | 6”x8”x20' | 20 | ft | 103.4 | 0.0868 | 112.3751 | 5.6188 | https://northlandwood.com/roughlumber/
Lumber Rough Sawn | 8”x8”x20' | 20 | ft | 136 | 0.0868 | 147.8048 | 7.3902 | https://northlandwood.com/roughlumber/
Pattern Stock Cedar Tongue and Groove Board | $ 15.88 per 1”x6”x12' | 6 | ft^2 | 15.88 | 0.0868 | 17.2584 | 2.8764 | http://www.homedepot.com/p/Pattern-Stock-Cedar-Tongue-and-Groove-Board-Common-1-in-x-6-in-x-12-ft-Actual-0-625-in-x-5-37-in-x-144-in-906909/100071949
1/4 in. x 3.5 in. 14 sq. ft. Western Cedar Planks | $19.75 per .25”x3.5” (14ft^2) | 14 | ft^2 | 19.75 | 0.0868 | 21.4643 | 1.5332 | http://www.homedepot.com/p/1-4-in-x-3-5-in-14-sq-ft-Western-Cedar-Planks-6-Pack-8203015/202106509
1/4 in. x 3-3/4 in. x 48 in. 100% Aromatic Eastern Red Cedar Planking | $27.47 .25”x3.75”x48” | 1.25 | ft^2 | 27.47 | 0.0868 | 29.8544 | 23.8835 | http://www.homedepot.com/p/1-4-in-x-3-3-4-in-x-48-in-100-Aromatic-Eastern-Red-Cedar-Planking-36422/205667315
Plywood 23/32 TG 4x8 plywood | $32.38 bulk $ 35.98 each /sheet | 32 | ft^2 | 32.38 | 0.0868 | 35.1906 | 1.0997 | http://www.homedepot.com/p/23-32-in-x-4-ft-x-8-ft-Southern-Pine-Tongue-and-Groove-Plywood-Sheathing-724084/100003769
Plywood 15/32 RTD Sheathing | $22.73 bulk $ 25.25 each /sheet | 32 | ft^2 | 22.73 | 0.0868 | 24.703 | 0.77197 | http://www.homedepot.com/p/15-32-in-x-4-ft-x-8-ft-3-Ply-RTD-Sheathing-166073/100067329
Plywood 19/32 RTD Sheathing | $25.35 bulk $28.17 each /sheet | 32 | ft^2 | 25.35 | 0.0868 | 27.5504 | 0.86095 | http://www.homedepot.com/p/19-32-in-x-4-ft-x-8-ft-Rtd-Sheathing-Syp-166081/100004472
Plywood 23/32 RTD Sheathing | $29.23 bulk $32.48 each / sheet | 32 | ft^2 | 29.23 | 0.0868 | 31.7672 | 0.99272 | http://www.homedepot.com/p/23-32-in-x-4-ft-x-8-ft-RTD-Sheathing-Syp-166103/100041308
OSB 7/16 | $17.15 bulk $19.05 each /sheet | 32 | ft^2 | 17.15 | 0.0868 | 18.6386 | 0.58246 | http://www.homedepot.com/p/7-16-in-x-48-in-x-8ft-Oriented-Strand-Board-386081/202106230
Sheathing Clip | $7.87 per 50 | 50 | each | 7.87 | 0.0868 | 8.5531 | 0.17106 | https://www.homedepot.com/p/Simpson-Strong-Tie-20-Gauge-5-8-in-Plywood-Sheathing-Clip-50-Qty-PSCL-5-8-R50/100375083
TJI | 1.5 x 9 ½ | 1 | ft | 2.25 | 0.0868 | 2.4453 | 2.4453 | http://www.northlandwood.com/lam.htm
TJI | 1.5 x 11 7/8 | 1 | ft | 2.4 | 0.0868 | 2.6083 | 2.6083 | http://www.northlandwood.com/lam.htm
TJI | 1.5 x 11 7/8 | 1 | ft | 2.45 | 0.0868 | 2.6627 | 2.6627 | Foxworth Galbrath 928-445-2525 2/15/17
TJI | 1.5 x 16 | 1 | ft | 3.4 | 0.0868 | 3.6951 | 3.6951 | http://www.northlandwood.com/lam.htm
14” TJI | 14” | 1 | ft | 2.07 | 0.0868 | 2.2497 | 2.2497 | http://www.acehardware.net/estimate/
14” TJI | 14” | 1 | ft | 2.6 | 0.0868 | 2.8257 | 2.8257 | GUESS
Rim Board | 11 7/8” | 1 | ft | 4.95 | 0.0868 | 5.3797 | 5.3797 | https://northlandwood.com/joists_beams_lams/
Rim Board | 11 7/8” | 12 | ft | 24 | 0.0868 | 26.0832 | 2.1736 | https://www.menards.com/main/building-materials/trusses-i-joists-engineered-lumber/i-joists-rim-boards/lp-reg-1-1-8-x-12-rim-board/p-1444438245882.htm
LVL (Laminated Veneer Lumber) | 1 ¾ X 7 1/4 3100FB 2.0E | 1 | ft | 4.45 | 0.0868 | 4.8363 | 4.8363 | https://www.goodrichlumber.com/MainSite/Store1/StoreProducts/ProductDetail/1475
LVL (Laminated Veneer Lumber) | 1 ¾ X 11 7/8 3100FB 2.0E | 1 | ft | 5.91 | 0.0868 | 6.423 | 6.423 | https://www.goodrichlumber.com/MainSite/Store1/StoreProducts/ProductDetail/1471
LVL (Laminated Veneer Lumber) | 1 ¾ X 14 3100FB 2.0E | 1 | ft | 7.58 | 0.0868 | 8.2379 | 8.2379 | https://www.goodrichlumber.com/MainSite/Store1/StoreProducts/ProductDetail/1472
LVL (Laminated Veneer Lumber) | 1 ¾ – 2 X 14 | 1 | ft | 9.5 | 0.0868 | 10.3246 | 10.3246 | Foxworth Galbrath 928-445-2525 3/28/17
LVL (Laminated Veneer Lumber) | 1 ¾ X 18 | 1 | ft | 11.1 | 0.0868 | 12.0635 | 12.0635 | https://www.goodrichlumber.com/MainSite/Store1/StoreProducts/ProductDetail/1474
LVL (Laminated Veneer Lumber) | 1 ¾ X 18 – 2 | 1 | ft | 13.45 | 0.0868 | 14.6175 | 14.6175 | Foxworth Galbrath 928-445-2525 3/28/17
Gluelam Beam | 3 1/8 x 9 | 1 | ft | 10.5 | 0.0868 | 11.4114 | 11.4114 | http://www.northlandwood.com/lam.htm
Gluelam Beam | 3 1/8 x 12 | 1 | ft | 6.6 | 0.0868 | 7.1729 | 7.1729 | http://www.northlandwood.com/lam.htm
Gluelam Beam | 5 1/8 x 12 | 1 | ft | 21.45 | 0.0868 | 23.3119 | 23.3119 | http://www.northlandwood.com/lam.htm
Gluelam Beam | 5 1/8 x 15 | 1 | ft | 26.4 | 0.0868 | 28.6915 | 28.6915 | http://www.northlandwood.com/lam.htm
Gluelam Beam | 5 1/8 x 18 | 1 | ft | 32.45 | 0.0868 | 35.2667 | 35.2667 | http://www.northlandwood.com/lam.htm
Gluelam Beam | 5 1/2 x 11 7/8 | 1 | ft | 14.48 | 0.0868 | 15.7369 | 15.7369 | Weyerhaeuser, Foxworth Galbrath 928-445-2525 3/28/17
Gluelam Beam | 5 ½ x 16 ½ | 1 | ft | 18 | 0.0868 | 19.5624 | 19.5624 | Guess
Gluelam Beam | 5 ½ x 24 | 1 | ft | 30 | 0.0868 | 32.604 | 32.604 | Guess
Gluelam Beam | 6 3/4 x 24 | 1 | ft | 50 | 0.0868 | 54.34 | 54.34 | Guess
Gluelam Beam | 8 3/4 x 24 | 1 | ft | 67.86 | 0.0868 | 73.7502 | 73.7502 | Capitol, Foxworth Galbrath 928-445-2525 3/28/17
VERSALAM COL | 3 ½ X 3 ½ | 1 | ft | 5.87 | 0.0868 | 6.3795 | 6.3795 | https://www.goodrichlumber.com/MainSite/Store1/StoreProducts/ProductDetail/5
Paralam Column | 7”x7” | 1 | ft | 20 | 0.0868 | 21.736 | 21.736 | guess
Joist Hanger | $0.96/each | 1 | each | 0.96 | 0.0868 | 1.0433 | 1.0433 | http://www.homedepot.com/p/Simpson-Strong-Tie-Z-MAX-2-in-x-6-in-Galvanized-Double-Shear-Face-Mount-Joist-Hanger-LUS26Z/100375105
Glue Sub-floor | $4.33 @ 12oz/85ft | 85 | ft | 4.33 | 0.0868 | 4.7058 | 0.055363 | http://www.homedepot.com/p/Liquid-Nails-28-oz-Subfloor-and-Deck-Construction-Adhesive-12-Pack-LNP-902-CP/202246452
Nails Framing 3-1/4” | $50.93/4000 | 4000 | each | 50.93 | 0.0868 | 55.3507 | 0.013838 | http://www.homedepot.com/p/Grip-Rite-3-1-4-in-x-0-131-Plastic-Bright-Vinyl-Coated-Steel-Smooth-Shank-Round-Framing-Nails-4-000-per-Box-GR024/100394345
Pier Post Base | $10.37/each | 1 | each | 10.37 | 0.0868 | 11.2701 | 11.2701 | http://www.homedepot.com/p/Simpson-Strong-Tie-4-in-x-4-in-12-Gauge-Hot-Dip-Galvanized-Pier-Block-Elevated-Post-Base-EPB44PHDG/100506799?cm_mmc=Shopping%7cTHD%7cG%7c0%7cG-BASE-PLA-D22-BuildingMaterials%7c&gclid=CLr6kMf-jNACFYF6fgodw9cMSw&gclsrc=aw.ds
Cement, Surface Bonding, QuickWall | $20.87/50ft^2 | 50 | ft^2 | 20.87 | 0.0868 | 22.6815 | 0.45363 | https://www.lowes.com/pd/QUIKRETE-Quikwall-50-lb-White-Cement-Mix/3006092
R-19 Insulation Fiberglass (Roll) | $28.19/48.96ft&2 (15”x39.2') | 48.96 | ft^2 | 19.73 | 0.0868 | 21.4426 | 0.43796 | http://www.homedepot.com/p/Owens-Corning-R-19-Kraft-Faced-Insulation-Continuous-Roll-15-in-x-39-2-ft-RF40/202585898
R-19 Insulation Fiberglass (Batt) | $45.48/77.5^ft2 | 77.5 | ft^2 | 31.84 | 0.0868 | 34.6037 | 0.4465 | http://www.homedepot.com/p/Owens-Corning-R-19-Kraft-Faced-Insulation-Batts-15-in-x-93-in-BF40/202585865
R-19 Insulation Cellulose (Blown) | $9.07/40fr^2 | 40 | ft^2 | 9.07 | 0.0868 | 9.8573 | 0.24643 | http://www.homedepot.com/p/GreenFiber-Low-Dust-Cellulose-Blow-in-Insulation-19-lbs-Bag-INS541LD/100318635
R-21 Insulation Fiberglass (Batt) | $629.09/678.10 | 678.1 | ft^2 | 629.09 | 0.0868 | 683.695 | 1.0083 | http://www.homedepot.com/p/Owens-Corning-R-21-Insulation-Kraft-Faced-Batts-15-in-x-93-in-10-Bags-BF60/205470953
R-30 Insulation Fiberglass (Batt) | $80.98 per 88ft^2 | 88 | ft^2 | 80.98 | 0.0868 | 88.0091 | 1.0001 | http://www.homedepot.com/p/Owens-Corning-R-30-Kraft-Faced-Insulation-Batts-24-in-x-48-in-BF71/202585885
R38 Insulation Unfaced Batts 24 in. x 48 in. 12” thick (8-Bags) | $857.68 per 8-bags (512 ft^2) | 512 | ft^2 | 857.68 | 0.0868 | 932.1266 | 1.8206 | http://www.homedepot.com/p/Owens-Corning-R38-Insulation-Unfaced-Batts-24-in-x-48-in-8-Bags-BU81/205471557
R49 Fiberglass Batt 24”x48”x14” | $72 per 48ft^2 30% off for 15 or more | 48 | ft^2 | 51 | 0.0868 | 55.4268 | 1.1547 | https://www.lowes.com/pd/Owens-Corning-R49-48-sq-ft-Faced-Fiberglass-Batt-Insulation-with-Sound-Barrier-24-in-W-x-48-in-L/1000085517
R49 Insulation Fiberglass (Blown) | $34.98/39.5ft^2 | 34.98 | ft^2 | 34.98 | 0.0868 | 38.0163 | 1.0868 | http://www.homedepot.com/p/Owens-Corning-AttiCat-Fiberglass-Expanding-Blown-in-Insulation-System-L38A/100541755
Cellulose (Blown) | $447.78 per 36 bags / 60ft^2 per 30lb bag @R-19 | 1 | ft^2 |  | 0.0868 | 0 | 0 | http://www.homedepot.com/p/GreenFiber-All-Borate-Cellulose-Blow-in-Insulation-30-lbs-36-Pallet-INS765LD/300584221
Cellulose (Blown) @ R19 | 12.4383 | 1 | ft^2 | 0.20731 | 0.0868 | 0.2253 | 0.2253 | http://www.homedepot.com/p/GreenFiber-All-Borate-Cellulose-Blow-in-Insulation-30-lbs-36-Pallet-INS765LD/300584221
Cellulose (Blown) @ R40 |  | 1 | ft^2 | 0.43643 | 0.0868 | 0.47432 | 0.47432 | http://www.homedepot.com/p/GreenFiber-All-Borate-Cellulose-Blow-in-Insulation-30-lbs-36-Pallet-INS765LD/300584221
Netting for Blown in Insulation | $483.13 / 8' x 750' | 6000 | ft^2 | 483.13 | 0.0868 | 525.0657 | 0.087511 | https://www.menards.com/main/building-materials/insulation/insulation-accessories/hanes-insulweb-reg-8-x-750-netting/p-1444423325023-c-5776.htm?tid=7954070246513455495&ipos=2
R-10 Rigid Foam Insulation | $39.95/ 2”x4'x8' sheet | 32 | ft^2 | 39.95 | 0.0868 | 43.4177 | 1.3568 | http://www.homedepot.com/p/Owens-Corning-FOAMULAR-250-2-in-x-48-in-x-8-ft-R-10-Scored-Squared-Edge-Insulation-Sheathing-52DD/202085962
R-13.1 Ridgid Insulation Rmax Thermasheath-3 2 in. x 4 ft. x 8 ft. R-13.1 Polyisocyanurate Rigid Foam Insulation Board | $34 single $30.60 bulk per sheet | 32 | ft^2 | 30.6 | 0.0868 | 33.2561 | 1.0393 | http://www.homedepot.com/p/Thermasheath-Rmax-Thermasheath-3-2-in-x-4-ft-x-8-ft-R-13-1-Polyisocyanurate-Rigid-Foam-Insulation-Board-613010/100573703
R-3.2 Rmax Plus-3 1/2 in. x 4 ft. x 8 ft. R-3.2 Polyisocyanurate Rigid Foam Insulation Board | $20.75 per sheet | 32 | ft^2 | 20.75 | 0.0868 | 22.5511 | 0.70472 | http://www.homedepot.com/p/Thermasheath-Rmax-Thermasheath-3-2-in-x-4-ft-x-8-ft-R-13-1-Polyisocyanurate-Rigid-Foam-Insulation-Board-613010/100573703
20 Mil Crawl Space Vapor Barrier | 309.25/ 13'4”x50' | 650 | ft^2 | 309.25 | 0.0868 | 336.0929 | 0.51707 | https://crawlspacerepair.com/20-mil-vapor-barrier-for-crawl-space-encapsulation
Vapor Barrier Tape for Crawl Space | $32.99/ 500ft^2 of area | 500 | ft^2 | 32.99 | 0.0868 | 35.8535 | 0.071707 | https://crawlspacerepair.com/waterproof-seam-tape-for-crawl-space-vapor-barrier
Foundation Seal Tape | $25.99 / 108ft | 25.99 | ft | 25.99 | 0.0868 | 28.2459 | 1.0868 | https://crawlspacerepair.com/foundation-seal-tape-for-crawl-spaces
Crawl Space Ventilator LM-CSVENT-PCV1 | 119 | 1 | each | 119 | 0.0868 | 129.3292 | 129.3292 | http://www.rewci.com/crspve110cfm.html
Tyvek 3'x165' | $66.25/3x165 | 445.5 | ft^2 | 66.25 | 0.0868 | 72.0005 | 0.16162 | http://www.homedepot.com/p/TYVEK-HomeWrap-3-ft-x-165-ft-Roll-Housewrap-D14050353/100422452
Tyvek 9'x150' | $165/each | 1350 | ft^2 | 165 | 0.0868 | 179.322 | 0.13283 | http://www.homedepot.com/p/TYVEK-HomeWrap-9-ft-x-150-ft-Roll-Housewrap-D13499991/100422450
Tyvek Tape | $13.25/164ft | 164 | ft | 13.25 | 0.0868 | 14.4001 | 0.087805 | http://www.homedepot.com/p/TYVEK-HomeWrap-2-in-x-164-ft-Installation-Tape-D13841470/100422453
Hardie Board Cement Board Siding | $8.72/each (144x8.25 @ 1.25” overlap) | 7 | ft^2 | 8.72 | 0.0868 | 9.4769 | 1.3538 | http://www.homedepot.com/p/James-Hardie-HardiePlank-HZ10-5-16-in-x-8-25-in-x-144-in-Fiber-Cement-Select-Cedarmill-Lap-Siding-215518/100064049
Hardie oard Vented Soffit | $27.74 / 24”x96” | 16 | ft^2 | 27.74 | 0.0868 | 30.1478 | 1.8842 | https://www.lowes.com/pd/James-Hardie-24-in-x-96-in-HardieSoffit-Primed-Fiber-Cement-Vented-Soffit/3109037
Hardie Board Trim | 13.65 / 1”x3.5”x144” | 12 | ft | 13.65 | 0.0868 | 14.8348 | 1.2362 | http://www.homedepot.com/p/James-Hardie-HardieTrim-HZ10-1-0-in-x-3-5-in-x-144-in-Fiber-Cement-Rustic-Grain-Trim-Board-216660/100015060
11-ga Roofing Nail 1-1/4” | $32.24/7200 | 7200 | each | 32.24 | 0.0868 | 35.0384 | 0.0048664 | http://www.homedepot.com/p/Freeman-1-1-4-in-11-Gauge-Roofing-Nails-RN-125/203502962
Exterior Paint | $45.98/gal @300ft^2/gal | 200 | gal | 45.98 | 0.0868 | 49.9711 | 0.24986 | http://www.homedepot.com/p/BEHR-MARQUEE-1-gal-PPU9-12-Prairie-House-Flat-Exterior-Paint-445001/204227324
Exterior Siding Nails | $88.67/4200 | 4200 | each | 88.67 | 0.0868 | 96.3666 | 0.022944 | http://www.homedepot.com/p/DEWALT-1-3-4-in-x-0-080-in-Galvanized-Metal-Ring-Shank-Coil-Nails-4200-Pieces-DWC5R80BDG/205647575
Window Large | 302.54 (72x48) | 1 | each | 302.54 | 0.0868 | 328.8005 | 328.8005 | http://www.homedepot.com/p/SIMONTON-72-in-x-48-in-DaylightMax-Left-Hand-Sliding-Vinyl-Window-White-DMSL-7248WHL2CAARHS/204740889?keyword=204740889
Window Medium | 295.05 (59.5x47.5) | 1 | each | 295.05 | 0.0868 | 320.6603 | 320.6603 | http://www.homedepot.com/p/JELD-WEN-59-5-in-x-47-5-in-V-2500-Series-Right-Hand-Sliding-Vinyl-Window-with-Grids-White-THDJW138500117/205817786?keyword=205817786
Window Small | 140.93(23.5x35.5) | 1 | each | 140.93 | 0.0868 | 153.1627 | 153.1627 | http://www.homedepot.com/p/JELD-WEN-23-5-in-x-35-5-in-V-2500-Series-Right-Hand-Sliding-Vinyl-Window-with-Grids-White-THDJW138500053/205817737?keyword=205817737
Window | 96x48" | 1 | each | 460.05 | 0.0868 | 499.9823 | 499.9823 | http://www.homedepot.com/p/SIMONTON-96-in-x-48-in-DaylightMax-Universal-Hand-End-Vent-Sliding-Vinyl-Window-White-DMEV-9648WHL2ARHS/204740938
Window | 60x48" | 1 | each | 331.72 | 0.0868 | 360.5133 | 360.5133 | http://www.homedepot.com/p/JELD-WEN-59-5-in-x-47-5-in-V-4500-Series-Left-Hand-Sliding-Vinyl-Windows-White-THDJW140400125/205818294
Window | 48x48" | 1 | each | 295.71 | 0.0868 | 321.3776 | 321.3776 | http://www.homedepot.com/p/JELD-WEN-47-5-in-x-47-5-in-V-4500-Series-Right-Hand-Sliding-Vinyl-Windows-White-THDJW140400105/205818292
Window | 48x24" | 1 | each | 263.41 | 0.0868 | 286.274 | 286.274 | http://www.homedepot.com/p/JELD-WEN-47-5-in-x-23-5-in-V-4500-Series-Awning-Vinyl-Window-White-THDJW140000447/205720398
Window | 36x36" | 1 | each | 199.24 | 0.0868 | 216.534 | 216.534 | http://www.homedepot.com/p/JELD-WEN-35-5-in-x-35-5-in-V-4500-Series-Fixed-Picture-Vinyl-Window-in-White-THDJW142100094/205807124
Window | 24x36" | 1 | each | 250.83 | 0.0868 | 272.602 | 272.602 | http://www.homedepot.com/p/JELD-WEN-23-5-in-x-35-5-in-V-4500-Series-Single-Hung-Vinyl-Window-Yellow-THDJW143900135/205688339
Window | 12x60" | 1 | each |  | 0.0868 | 0 | 0
Window | ? | 1 | each |  | 0.0868 | 0 | 0
Window | 36x48" | 1 | each | 256.06 | 0.0868 | 278.286 | 278.286 | http://www.homedepot.com/p/JELD-WEN-35-5-in-x-47-5-in-V-4500-Series-Single-Hung-Vinyl-Window-White-THDJW143900085/205688305
Front Door | 1150.31 | 1 | each | 1150.31 | 0.0868 | 1250.1569 | 1250.1569 | http://www.homedepot.com/p/Pacific-Entries-36-in-x-80-in-Craftsman-Rustic-6-Lite-Stained-Knotty-Alder-Wood-Prehung-Front-Door-A36R/205204220
Milgard Tuscany 4pnl Sliding Glass Door | 144x80" | 1 | each | 3000 | 0.0868 | 3260.4 | 3260.4 | Quote from Lowes in person
Cheap Sliding Glass Door 4pnl | 1768.35 | 1 | each | 1768.35 | 0.0868 | 1921.8428 | 1921.8428 | http://www.homedepot.com/p/SIMONTON-143-5-in-x-79-5-in-4-Panel-Contemporary-Vinyl-Sliding-Patio-Door-with-ProSolar-LowE-Glass-and-Custom-Interior-Hardware-CPD-14480WHL2ARFS/204860324?keyword=204860324
French Door | 72x80” | 1 | each | 1548.05 | 0.0868 | 1682.4207 | 1682.4207 | http://www.homedepot.com/p/JELD-WEN-72-in-x-80-in-Brilliant-White-Prehung-Left-Hand-Inswing-French-Patio-Door-with-Brickmould-and-Blinds-THDJW205900499/206873603
Exterior Door | $442.71/each | 1 | each | 442.71 | 0.0868 | 481.1372 | 481.1372 | http://www.homedepot.com/p/JELD-WEN-36-in-x-80-in-Craftsman-6-Lite-Primed-Premium-Steel-Prehung-Front-Door-with-Brickmould-and-Dentil-Shelf-N11437/203188829?keyword=203188829
Cheap Interior Door | $36.48/each | 1 | each | 36.48 | 0.0868 | 39.6465 | 39.6465 | http://www.homedepot.com/p/Masonite-36-in-x-80-in-Textured-6-Panel-Hollow-Core-Primed-Composite-Interior-Door-Slab-16931/100034895?keyword=100034895
Cheap Interior Pre-Hung Door | 75.95 | 1 | each | 75.95 | 0.0868 | 82.5425 | 82.5425 | http://www.homedepot.com/p/Masonite-36-in-x-80-in-6-Panel-Left-Handed-Hollow-Core-Textured-Primed-Composite-Single-Prehung-Interior-Door-07450/100084672
Fire Rated Door | 36x80” | 1 | each | 199 | 0.0868 | 216.2732 | 216.2732 | http://www.homedepot.com/p/JELD-WEN-36-in-x-80-in-6-Panel-Primed-20-Minute-Fire-Rated-Steel-Prehung-Left-Hand-Inswing-Front-Door-THDJW166100249/202036318
Single Prehung Interior Door Hemlock unfinished | 36x80” | 1 | each | 239 | 0.0868 | 259.7452 | 259.7452 | http://www.homedepot.com/p/Builder-s-Choice-36-in-x-80-in-6-Panel-Left-Hand-Hemlock-Single-Prehung-Interior-Door-HD66S30L/100096329
Single Prehung Interior Door Hemlock unfinished | 32x80” | 1 | each | 234 | 0.0868 | 254.3112 | 254.3112 | http://www.homedepot.com/p/Builder-s-Choice-36-in-x-80-in-6-Panel-Left-Hand-Hemlock-Single-Prehung-Interior-Door-HD66S30L/100096329
Single Prehung Interior Door Hemlock unfinished | 30x80” | 1 | each | 234 | 0.0868 | 254.3112 | 254.3112 | http://www.homedepot.com/p/Builder-s-Choice-36-in-x-80-in-6-Panel-Left-Hand-Hemlock-Single-Prehung-Interior-Door-HD66S30L/100096329
Pocket Door
Pocket Door
Bi-Folding Door | 28x80” | 1 | each | 128 | 0.0868 | 139.1104 | 139.1104 | http://www.homedepot.com/p/Home-Fashion-Technologies-28-in-x-80-in-6-Panel-Primed-Solid-Wood-Interior-Closet-Bi-Fold-Door-1602880200/202979493
Slab Door Clear Pine Unfinished | 24x80” | 1 | each | 128 | 0.0868 | 139.1104 | 139.1104 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-6-Panel-Clear-Pine-Interior-Door-Slab-HDCP6620/202532825
Slab Door Clear Pine Unfinished | 28x80” | 1 | each | 128 | 0.0868 | 139.1104 | 139.1104 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-6-Panel-Clear-Pine-Interior-Door-Slab-HDCP6620/202532825
Slab Door Clear Pine Unfinished | 30x80” | 1 | each | 119 | 0.0868 | 129.3292 | 129.3292 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-6-Panel-Clear-Pine-Interior-Door-Slab-HDCP6620/202532825
Slab Door Clear Pine Unfinished | 32x80” | 1 | each | 114 | 0.0868 | 123.8952 | 123.8952 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-6-Panel-Clear-Pine-Interior-Door-Slab-HDCP6620/202532825
Slab Door Clear Pine Unfinished | 36x80” | 1 | each | 118 | 0.0868 | 128.2424 | 128.2424 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-6-Panel-Clear-Pine-Interior-Door-Slab-HDCP6620/202532825
36” Pocket Door Frame | 32” | 1 | each | 83 | 0.0868 | 90.2044 | 90.2044 | http://www.homedepot.com/p/Builder-s-Choice-32-in-Pocket-Door-Frame-DFPDI428/100069123
Interior French Door Pine Unfinished Glass Panel | 72x80” | 1 | each | 618.93 | 0.0868 | 672.6531 | 672.6531 | http://www.homedepot.com/p/MMI-Door-73-5-in-x-81-75-in-Classic-Clear-True-Divided-15-Lite-Unfinished-Pine-Wood-Interior-French-Double-Door-Z019959BA/207061878
Interior Door Slab Hemlock 10 Lite Unfinished | 24x80” | 1 | each | 189 | 0.0868 | 205.4052 | 205.4052 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-Hemlock-10-Lite-Interior-Door-Slab-HD1510S20/202535849
Interior Door Slab Hemlock 10 Lite Unfinished | 36x80” | 1 | each | 209 | 0.0868 | 227.1412 | 227.1412 | http://www.homedepot.com/p/Builder-s-Choice-24-in-x-80-in-Hemlock-10-Lite-Interior-Door-Slab-HD1510S20/202535849
Garage Door Insulated 10x8 | 1100 | 1 | each | 1100 | 0.0868 | 1195.48 | 1195.48 | https://www.menards.com/main/doors-windows-millwork/exterior-doors/garage-doors-garage-door-openers/shop-all-garage-doors/ideal-door-reg-5-star-10-ft-x-8-ft-sandtone-premium-insulated-garage-door-with-madison-arch-windows/p-1491373311666-c-12358.htm?tid=-1743057851000207352&ipos=6
Garage Door Insulated 16x8 | 1009 | 1 | each | 1009 | 0.0868 | 1096.5812 | 1096.5812 | https://www.menards.com/main/doors-windows-millwork/exterior-doors/garage-doors-garage-door-openers/shop-all-garage-doors/ideal-door-reg-sunrise-16-ft-x-8-ft-4-star-desert-tan-insul-ez-set-reg-garage-door/p-1444433874494-c-12358.htm?tid=8557660199318680604&ipos=1
Shop Door 10'x10' Insulated | 774 | 1 | each | 774 | 0.0868 | 841.1832 | 841.1832 | https://www.menards.com/main/doors-windows-millwork/exterior-doors/garage-doors/garage-doors/ideal-door-reg-5-star-10-x-10-white-commercial-premium-insulated-garage-door/p-1444433900651-c-12358.htm?tid=-3410685420619682194&ipos=8
Shop Door 10'x14' Insulated | 1000 | 1 | each | 1000 | 0.0868 | 1086.8 | 1086.8 | https://www.menards.com/main/doors-windows-millwork/exterior-doors/garage-doors/garage-doors/ideal-door-reg-4-star-10-x-14-white-commercial-insulated-garage-door/p-1444433860578-c-12358.htm?tid=-2555219637433344797&ipos=2
Garage Door Opener | 244 | 1 | each | 244 | 0.0868 | 265.1792 | 265.1792 | http://www.homedepot.com/p/Chamberlain-1-1-4-HPS-Smartphone-Controlled-Wi-Fi-Belt-Drive-Garage-Door-Opener-with-Battery-Backup-and-Ultra-Quiet-Operation-HD950WF/205880822
Door Knob Passage | 16.32 | 1 | each | 16.32 | 1.0868 | 34.0566 | 34.0566 | http://www.homedepot.com/p/Kwikset-Cove-Antique-Brass-Bed-Bath-Knob-300CV-5-RCAL-RCS/203274878
Door Knob Privacy | 14.78 | 1 | each | 14.78 | 2.0868 | 45.6229 | 45.6229 | http://www.homedepot.com/p/Kwikset-Cove-Venetian-Bronze-Hall-Closet-Knob-200CV-11P-6AL-RCS/202106268
Door Knob Entry | 49.92 | 1 | each | 49.92 | 3.0868 | 204.0131 | 204.0131 | http://www.homedepot.com/p/Kwikset-Juno-Satin-Nickel-Exterior-Entry-Knob-and-Single-Cylinder-Deadbolt-Combo-Pack-featuring-SmartKey-991J-15-SMT-CP/100597328
Metal Roof Sheet | $45.98/16'x3' | 48 | ft^2 | 45.98 | 0.0868 | 49.9711 | 1.0411 | http://www.homedepot.com/p/Metal-Sales-16-ft-Classic-Rib-Steel-Roof-Panel-in-Burnished-Slate-2313649/204255223
Metal Roofing | $150-300 per 10'x10' | 100 | ft^2 | 200 | 0.0868 | 217.36 | 2.1736 | ABC Building Supply 928-772-7141
Metal Drip Edge | $8.31 per 10ft | 10 | ft | 8.31 | 0.0868 | 9.0313 | 0.90313 | http://www.homedepot.com/p/Construction-Metals-2-in-x-3-in-x-10-ft-Roof-Edge-Flashing-in-White-RE23WH/202092739
Metal Roofing Screws | $9.68/100 | 100 | box | 9.68 | 0.0868 | 10.5202 | 0.1052 | http://www.homedepot.com/p/Teks-9-x-1-1-2-in-Zinc-Plated-Steel-Hex-Washer-Head-Roofing-Screws-100-Pack-21404/100188361
UDL Titanium 50 Roof Underlayment | $171.98 per 4'x250' roll | 1000 | ft^2 | 171.98 | 0.0868 | 186.9079 | 0.18691 | http://buymbs.com/p-100-titanium-udl-50-synthetic-underlayment.aspx?vid=98
Roof Under-layment | $178/225ft^2 | 225 | ft^2 | 178.1 | 0.0868 | 193.5591 | 0.86026 | http://www.homedepot.com/p/Grace-Ice-Water-Shield-36-in-x-75-ft-225-sq-ft-Roll-Roofing-Underlayment-in-Black-5003002/202088840
Drywall 1/2” | $10.47 / 8.90 bulk /sheet | 32 | ft^2 | 9.98 | 0.0868 | 10.8463 | 0.33895 | http://www.homedepot.com/p/Sheetrock-UltraLight-1-2-in-x-4-ft-x-8-ft-Gypsum-Board-14113411708/202530243
Drywall 5/8” | $12.57 / 10.68 bulk /sheet | 32 | ft^2 | 10.68 | 0.0868 | 11.607 | 0.36272 | http://www.homedepot.com/p/Sheetrock-Firecode-Core-5-8-in-x-4-ft-x-8-ft-Gypsum-Board-14211011308/100321591
Interior Primer | $13.98/gal (250-400 ft^2) | 300 | ft^2 | 13.98 | 0.0868 | 15.1935 | 0.050645 | http://www.homedepot.com/p/BEHR-Premium-Plus-1-gal-Drywall-Primer-and-Sealer-07301/100118531
Interior Paint | $32.98/gal (400 ft^2) | 400 | ft^2 | 32.98 | 0.0868 | 35.8427 | 0.089607 | http://www.homedepot.com/p/BEHR-Premium-Plus-Ultra-1-gal-Ultra-Pure-White-Semi-Gloss-Enamel-Interior-Paint-375001/203202285
Vinyl Flooring | $4/ft^2 | 1 | ft^2 | 4 | 0.0868 | 4.3472 | 4.3472
Hardwood Flooring | $5.49/ft^2 | 1 | ft^2 | 5.49 | 0.0868 | 5.9665 | 5.9665 | http://www.homedepot.com/p/Heritage-Mill-Oak-Golden-3-4-in-Thick-x-4-in-Wide-x-Random-Length-Solid-Real-Hardwood-Flooring-21-sq-ft-case-PF9679/206021887
Cheap Hardwood Flooring | $3.29/ft^2 | 1 | ft^2 | 3.29 | 0.0868 | 3.5756 | 3.5756 | https://www.homedepot.com/p/Blue-Ridge-Hardwood-Flooring-Oak-Honey-Wheat-3-4-in-Thick-x-2-1-4-in-Wide-x-Random-Length-Solid-Hardwood-Flooring-18-sq-ft-case-20476/206719811
Porcelain Tile | $3/ft^2 | 1 | ft^2 | 3 | 0.0868 | 3.2604 | 3.2604 | https://www.builddirect.com/p/MS-International-Porcelain-Tile-Veneto-Series--15004020
Cement Board 1/2” | $21.93 single or 19.77 bulk per sheet | 32 | ft^2 | 21.97 | 0.0868 | 23.877 | 0.74616 | http://www.homedepot.com/p/DUROCK-Next-Gen-1-2-in-x-4-ft-x-8-ft-Cement-Board-172968/202328849
Fortified Thin-Set Mortar | $14.47 per 50lb bag (100 ft^2) | 100 | ft^2 | 14.47 | 0.0868 | 15.726 | 0.15726 | http://www.homedepot.com/p/Custom-Building-Products-VersaBond-Gray-50-lb-Fortified-Thin-Set-Mortar-MTSG50/100162542?MERCH=REC-_-NavPLPHorizontal1_rr-_-NA-_-100162542-_-N
Grout Tile Floor | $9.97 per 7lb (192 ft^2) | 150 | ft^2 | 9.97 | 0.0868 | 10.8354 | 0.072236 | http://www.homedepot.com/p/Custom-Building-Products-Polyblend-548-Surf-Green-7-lb-Sanded-Grout-PBG5487-4/205939330
Drywall Screws | $6.47/250 | 1 | each | 0.01788 | 0.0868 | 0.019432 | 0.019432 | http://www.homedepot.com/p/Grip-Rite-8-x-1-1-2-in-Philips-Bugle-Head-Coarse-Thread-Sharp-Point-Drywall-Screws-1-lb-Pack-112CDWS1/100127330
Carpet | 4.68 | 1 | ft^2 | 4.68 | 0.0868 | 5.0862 | 5.0862 | https://lowes.stainmaster.com/product-details?gtin=00765894796919&ProductLine=stainmastertrusoft&Alternative=stainmasteractivefamily&Style=Textured%7CFrieze%7CPlush&Color=White%7CCream%7CBeige%7CBrown%7CTan%7CGold%7COrange%7CRed%7CBlack%7CGray&AnswerCode=01100001110001010
Cheap Carpet | 1.21 | 1 | ft^2 | 1.28 | 0.0868 | 1.3911 | 1.3911 | https://www.homedepot.com/p/TrafficMASTER-Thoroughbred-ll-Color-Morgan-Texture-12-ft-Carpet-EF286-316-1200/303256366
Carpet Padding | 0.89 | 1 | ft^2 | 0.89 | 0.0868 | 0.96725 | 0.96725 | https://www.lowes.com/pd/STAINMASTER-11-11-mm-Rebond-Carpet-Padding/50280767
Carpet Tack Strip | $19.99 per 400ft | 400 | ft^2 | 19.99 | 0.0868 | 21.7251 | 0.054313 | https://www.lowes.com/pd/Blue-Hawk-1-in-Blue-Tack-Strip/4755339
Drywall Tape | $1.98/250ft | 1 | ft | 0.00792 | 0.0868 | 0.0086075 | 0.0086075 | http://www.homedepot.com/p/Sheetrock-250-ft-Drywall-Joint-Tape-382175/100321613
Drywall Mud | $7.45/350ft^2 | 1 | box | 7.45 | 0.0868 | 8.0967 | 8.0967 | http://www.homedepot.com/p/SHEETROCK-Brand-3-5-Gal-All-Purpose-Pre-Mixed-Joint-Compound-380122/202329634
Vanity Single | 491 | 1 | each | 491 | 0.0868 | 533.6188 | 533.6188 | http://www.homedepot.com/p/Foremost-Naples-48-in-W-x-21-5-8-in-D-x-34-in-H-Vanity-Cabinet-Only-in-White-NAWA4821D/203984978?keyword=203984978
Vanity Double | 600 | 1 | each | 600 | 0.0868 | 652.08 | 652.08 | http://www.homedepot.com/p/Foremost-Naples-60-in-W-x-21-5-8-in-D-x-34-in-H-Vanity-Cabinet-Only-in-Warm-Cinnamon-NACA6021D/100508059?keyword=100508059
Vanity Sink Single | 290 | 1 | each | 290 | 0.0868 | 315.172 | 315.172 | http://www.homedepot.com/p/Avanity-31-in-x-22-in-Vitreous-China-Vanity-Top-with-Rectangular-Bowl-in-White-CUT31WT/202831380?keyword=202831380
Vanity Sink Double | 563 | 1 | each | 563 | 0.0868 | 611.8684 | 611.8684 | http://www.homedepot.com/p/KOHLER-Ceramic-Impression-61-in-Vitreous-China-Double-Vanity-Top-with-Basin-in-White-Impressions-K-2789-1-G81/205750611?keyword=205750611
Toilet | 168 | 1 | each | 168 | 0.0868 | 182.5824 | 182.5824 | http://www.homedepot.com/p/KOHLER-Cimarron-2-piece-1-28-GPF-Single-Flush-Round-Toilet-in-White-K-15409-0/203014123?keyword=203014123
Showers | 811 | 1 | each | 811 | 0.0868 | 881.3948 | 881.3948 | http://www.homedepot.com/p/DreamLine-Prime-36-in-x-36-in-x-74-75-in-Framed-Sliding-Shower-Enclosure-in-Chrome-with-Quarter-Round-Shower-Base-DL-6702-01CL/205156600?keyword=205156600
Shower Tub Assembly Cheap | 387 | 1 | each | 387 | 0.0868 | 420.5916 | 420.5916 | https://www.homedepot.com/p/Aquatic-60-in-x-30-in-x-72-in-1-piece-Direct-to-Stud-Tub-Shower-Wall-in-White-260330SPCL-WH/203910584
Bathtub 1 | 582 | 1 | each | 582 | 0.0868 | 632.5176 | 632.5176 | http://www.homedepot.com/p/American-Standard-Savona-5-ft-x-42-in-Reversible-Drain-Oval-Soaking-Bathtub-in-White-2903-002-020/202516540?keyword=202516540
Bathtub 2 | 359 | 1 | each | 359 | 0.0868 | 390.1612 | 390.1612 | http://www.homedepot.com/p/KOHLER-Villager-5-ft-Cast-Iron-Right-Hand-Drain-Rectangular-Apron-Front-Non-Whirlpool-Bathtub-in-White-K-716-0/100069783?keyword=100069783
Shower Tub | 529 | 1 | each | 529 | 0.0868 | 574.9172 | 574.9172 | http://www.homedepot.com/p/STERLING-All-Pro-60-in-x-30-in-x-72-3-4-in-Shower-Kit-with-Left-Drain-in-White-61040110-0/202101083?keyword=202101083
Sink Faucet | 129 | 1 | each | 129 | 0.0868 | 140.1972 | 140.1972 | http://www.homedepot.com/p/MOEN-Banbury-8-in-Widespread-2-Handle-High-Arc-Bathroom-Faucet-in-Spot-Resist-Brushed-Nickel-WS84924SRN/206883372?keyword=206883372
Shower Fixture | 129 | 1 | each | 129 | 0.0868 | 140.1972 | 140.1972 | http://www.homedepot.com/p/Delta-Porter-Single-Handle-3-Spray-Shower-Faucet-in-Brushed-Nickel-142984-BN-A/206202996?keyword=206202996
Medicine Cab | 93 | 1 | each | 93 | 0.0868 | 101.0724 | 101.0724 | http://www.homedepot.com/p/KOHLER-16-in-W-x-20-in-H-x-5-in-D-Aluminum-Recessed-Medicine-Cabinet-K-CB-CLR1620FS/100675408?keyword=100675408
Mirror | 57 | 1 | each | 57 | 0.0868 | 61.9476 | 61.9476 | http://www.homedepot.com/p/Home-Decorators-Collection-Gazette-32-in-L-x-24-in-W-Framed-Wall-Mirror-in-White-GAWM2432/203284745?keyword=203284745
Spray Foam Insulation Closed Cell | 734 |  | board ft | 1.2233 | 0.0868 | 1.3295 | #DIV/0! | http://www.homedepot.com/p/Touch-n-Foam-600-Board-ft-Polyurethane-2-Component-Spray-Foam-Kit-4006062600/204962775
Primed Finger-Jointed Base Molding | 3.54 | 8 | each | 3.54 | 0.0868 | 3.8473 | 0.48091 | http://www.homedepot.com/p/Woodgrain-Millwork-WM-623-9-16-in-x-3-1-4-in-x-96-in-Primed-Finger-Jointed-Base-Moulding-10000558/203209372
Shop Steel Man Door | 162 | 1 | each | 162 | 0.0868 | 176.0616 | 176.0616 | http://www.homedepot.com/p/Masonite-36-in-x-80-in-Premium-Flush-Primed-Steel-Prehung-Front-Door-with-No-Brickmould-84178/204759995
Shop Windows | 47.66 | 1 | each | 47.36 | 0.0868 | 51.4708 | 51.4708 | http://www.homedepot.com/p/TAFCO-WINDOWS-23-5-in-x-23-5-in-Utility-Left-Hand-Single-Sliding-Vinyl-Window-White-VUS2424OP/100660072
Simpson Strong-Tie 1-1/4”x24” 20-GA | 1.67/each | 1 | each | 1.67 | 0.0868 | 1.815 | 1.815 | http://www.homedepot.com/p/Simpson-Strong-Tie-1-1-4-in-x-24-in-20-Gauge-Strap-LSTA24/100375306?keyword=lsta24+strap
Simpson IUS1.81/11.88 1-3/4 in. x 11-7/8 in. Face Mount I-Joist Hanger | $4.89/ each | 1 | each | 4.89 | 0.0868 | 5.3145 | 5.3145 | http://www.homedepot.com/p/Simpson-Strong-Tie-1-3-4-in-x-11-7-8-in-Face-Mount-I-Joist-Hanger-IUS1-81-11-88/203302218?keyword=IUS1.81%2F11.88
Simpson U210R Rough Sawn 2x12 Face Mount Hanfer | $4.15/each | 1 | each | 4.15 | 0.0868 | 4.5102 | 4.5102 | http://www.homedepot.com/p/Simpson-Strong-Tie-2-in-x-10-in-Rough-Face-Mount-Hanger-U210R/203302261?keyword=U210R
[5 empty] | 0.0868 | 0
Clothes Washer (Stackable) |  | 1 | each | 727.2 | 0.0868 | 790.321 | 790.321 | http://www.homedepot.com/p/LG-Electronics-4-5-cu-ft-High-Efficiency-Front-Load-Washer-with-Steam-in-Graphite-Steel-ENERGY-STAR-WM3670HVA/207024837?keyword=WM3670HVA
Clothes Dryer (Stackable) |  | 1 | each | 828 | 0.0868 | 899.8704 | 899.8704 | http://www.homedepot.com/p/LG-Electronics-7-4-cu-ft-Gas-Dryer-with-Steam-in-Graphite-Steel-ENERGY-STAR-DLGX3371V/205635528?keyword=DLGX3371V
Dishwasher |  | 1 | each | 898.2 | 0.0868 | 976.1638 | 976.1638 | http://www.homedepot.com/p/KitchenAid-Architect-Series-II-Top-Control-Dishwasher-in-Stainless-Steel-with-Stainless-Steel-Tub-Ultra-Fine-Filter-43-dBA-KDTM354DSS/205397273
Refrigerator |  | 1 | each | 1399 | 0.0868 | 1520.4332 | 1520.4332 | http://www.homedepot.com/p/GE-25-4-cu-ft-Side-by-Side-Refrigerator-in-Stainless-Steel-GSS25GSHSS/205599120
Tankless Propane Water Heater |  | 1 | each | 1201.33 | 0.0868 | 1305.6054 | 1305.6054 | http://www.homedepot.com/p/Rheem-8-4-GPM-Liquid-Propane-Gas-High-Efficiency-Indoor-Tankless-Water-Heater-ECOH160DVLP-1/206934537
Water Heater Pump & Control |  | 1 | each | 387 | 0.0868 | 420.5916 | 420.5916 | https://www.fasterhotwater.com/WQT%20coupon-code.php
Gas Range Top |  | 1 | each | 899 | 0.0868 | 977.0332 | 977.0332 | http://www.homedepot.com/p/Thor-Kitchen-36-in-Gas-Cooktop-in-Stainless-Steel-with-6-Burners-HRT3618U/300795394
Electric Double Oven |  | 1 | each | 1698 | 0.0868 | 1845.3864 | 1845.3864 | http://www.homedepot.com/p/Whirlpool-Gold-30-in-Double-Electric-Wall-Oven-Self-Cleaning-with-Convection-in-Stainless-Steel-WOD93EC0AS/203607911
Wood Stove |  | 1 | each | 1749 | 0.0868 | 1900.8132 | 1900.8132 | http://www.woodlanddirect.com/Wood-Stove-and-Accessories/Wood-Stoves-Large-Over-2000-sqft/Osburn-2300-Wood-Stove
Fireplace |  | 1 | each | 898.2 | 0.0868 | 976.1638 | 976.1638 | http://www.woodlanddirect.com/Wood-Stove-and-Accessories/Wood-Stoves-Large-Over-2000-sqft/Osburn-2300-Wood-Stove
Range Hood |  | 1 | each | 259 | 0.0868 | 281.4812 | 281.4812 | http://www.homedepot.com/p/AKDY-30-in-Under-Cabinet-Range-Hood-in-Stainless-Steel-with-LEDs-and-Electronic-Push-Buttons-HD-RH0235/300317580
Water Softener |  | 1 | each | 1377.49 | 0.0868 | 1497.0561 | 1497.0561 | http://www.homedepot.com/p/Pelican-Water-48-000-Grain-Heavy-Duty-Water-Softener-PLS48/301687666
Reverse Osmosis Water Filtration System |  | 1 | each | 511.96 | 0.0868 | 556.3981 | 556.3981 | http://www.homedepot.com/p/ISPRING-Dual-Flow-500-GPD-Commercial-Grade-Tankless-Under-Sink-Reverse-Osmosis-Water-Filtration-System-w-1-1-Filter-Drain-Ratio-RCS5T/2065044971 | each | 259 | 0.0868 | 281.4812 | #VALUE!
Sewage Pump |  | 1 | each | 411.81 | 0.0868 | 447.5551 | 447.5551 | https://www.homedepot.com/p/Liberty-Pumps-Pro380-Series-4-10-HP-Submersible-Pre-Assembled-Simplex-Sewage-System-with-LE41-Pump-24-in-x-24-in-Polyethylene-Basin-P382LE41/302038781
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
Elgin B43 Pad With Fabric and Clamps |  | 1 | each | 108 | 0.0868 | 117.3744 | 117.3744 | Bushnell Investments 3587 South Meridian, Apache Junction, AZ 85217 Contact: Roger Bushnell Phone: (480) 206-6811
Elgin A42 Pad With Fabric and Clamps |  | 1 | each | 88 | 0.0868 | 95.6384 | 95.6384 | Bushnell Investments 3587 South Meridian, Apache Junction, AZ 85217 Contact: Roger Bushnell Phone: (480) 206-6811
Concrete Sand $21/Ton |  | 1 | Ton | 21 | 0.0868 | 22.8228 | 22.8228 | http://www.prescottdirt.com/portfolio-item/concrete-sand/
4-in x 10-ft Perforated PVC Sewer Drain Pipe |  | 10 | ft | 9.99 | 0.0868 | 10.8571 | 1.0857 | https://www.lowes.com/pd/4-in-x-10-ft-Perforated-PVC-Sewer-Drain-Pipe/3449536
4 in. x 20 ft. PVC Sewer Main SDR 35 Pipe with Gasket |  | 10 | ft | 14.98 | 0.0868 | 16.2803 | 1.628 | https://www.lowes.com/pd/Charlotte-Pipe-4-in-x-10-ft-Solid-PVC-Sewer-Drain-Pipe/3133159
Quick 4 Plus HC Chamber |  | 1 | each | 32.99 | 0.0868 | 35.8535 | 35.8535 | https://hughessupply.com/prescott/
Quick 4 Plus Endcap |  | 1 | each | 17 | 0.0868 | 18.4756 | 18.4756 | https://hughessupply.com/prescott/
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
[5 empty] | 0.0868 | 0
0
0
0
0
0

## Total Budget
Total Construction Budget 10-30-17
ITEM NAME | MATERIALS | OUTSOURCED LABOR | FEES | EQUIPMENT | TOTAL | MAN HRS
Land |  |  |  |  | 0 | 0
Design & Engineering → See Contingency |  |  |  |  | 0 | 0
Building Permits & Fees |  |  | 5000 |  | 5000 | 0
Soil Test → See Contingency |  |  | 2000 |  | 2000 | 16
APS Power Connection |  | 2000 |  |  | 2000 | 16
Septic | 12859.5832 |  | 360.5 |  | 13220.0832 | 140
Well Water Line |  | 1000 |  |  | 1000 | 40
Grade Lot |  |  | 37.5 |  | 37.5 | 40
Misc Equipment Rental |  |  |  | 1000 | 1000 | 0
Power Tools |  |  |  | 1000 | 1000 | 0
Shop Construction | 65149.0468 | 1798.676 | 0 | 693 | 67640.7228 | 554
House Construction | 263158.9009 | 10800 |  | 0 | 273958.9009 | 2056
Cleanup |  |  | 200 |  | 200 | 40
Total | 341167.531 | 15598.676 | 7598 | 2693 | 367057.207 | 2902
10% Contingency | 34116.7531 | 1559.8676 | 759.8 | 269.3 | 36705.7207 | 290.2
Total with 10% Contingency | 375284.284 | 17158.5436 | 8357.8 | 2962.3 | 403762.9277 | 3192.2